Leashed

Program Delivery Guide

Implementation plan, pathway syllabi and instructor resources for the six integrated animal-care pathways

| Edition | v1.0 — September 2026 (companion to the Leashed Integrated Course Catalog v3.2) |
| --- | --- |
| Audience | Director, registrar, instructors, personal readiness coach, technology lead |
| Part A | Implementation plan — phases, calendar, staffing, facilities, content backlog, controls, KPIs |
| Part B | Pathway syllabi — IPDG, PDT, ACA, PPS, CAT, PPC (term outline, week-by-week schedule, assessment, texts) |
| Part C | Instructor and platform-facing sources; review sign-off form |
| Governing rules | Clock-hour unit, module evidence, rubric and safety gates are defined in the Leashed Integrated Course Catalog v3.2 and are not restated here |
| Prepared for | Etnologic Inc — Leashed, Shreveport, Louisiana |

# Contents

Contents

Part A — Implementation Plan

A1. Program Summary

A2. Rollout Phases

A3. Delivery Calendar by Program

A4. Weekly Schedule Template (full-time)

A5. Staffing Model

A6. Facilities Readiness

A7. Content Build Backlog

A8. Assessment & Clock-Hour Controls

A9. AI / RAG Ingestion Steps

A10. Launch KPIs

Part B — Pathway Syllabi

B1. Syllabus — Professional Dog Groomer IIPDG

B2. Syllabus — Professional Dog Trainer (PDT)

B3. Syllabus — Animal Care Assistant ACA

B4. Syllabus — Professional Pet Sitter PPS

B5. Syllabus — Professional Cat Groomer (CAT)

B6. Syllabus — Professional Pet Care & Business Ownership PPC

Part C — Instructor & Platform Sources

C1. Instructor and Platform-Facing Sources (SYS)

C2. Core Program Manuals — Build Status

Appendix — Instructor Review Sign-Off

Home / Academy/ Software / Pricing / About / Resources / Support

- Training

- Pathway

- Courses

ACADEMHY

TRAINING

PATHWAY

COURSES

# Part A — Implementation Plan

## A1. Program Summary

| Code | Program | Technical | Business & personal | Applied | Total hrs | Sched. wks | Credential |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IPDG | Professional Dog Groomer | 12 mod · 360 hr | 144 mod · 864 hr | 24 hr | 1,248 | 44 | Professional Dog Groomer Diploma |
| PDT | Professional Dog Trainer | 10 mod · 224 hr | 144 mod · 864 hr | 24 hr | 1,112 | 39 | Professional Dog Trainer Diploma |
| ACA | Animal Care Assistant | 5 mod · 112 hr | 144 mod · 864 hr | 12 hr | 988 | 35 | Dog Bather–Animal Care Assistant Diploma |
| PPS | Professional Pet PPSitter | 4 mod · 14 hr | 6 mod · 36 hr | 6 hr | 56 | 2 | Pet PPSitter Certificate |
| CAT | Professional Cat Groomer | 4 mod · 16 hr | 6 mod · 36 hr | 6 hr | 58 | 2 | Professional Cat Groomer Certificate |
| PPC | Professional Pet Care & Business Ownership | 27 mod · 600 hr | 144 mod · 864 hr | 36 hr | 1,500 | 52 | Professional Pet Care & Business Ownership — Advanced Diploma |

Scheduled weeks = one term per level, each term rounded up to whole 30-hour weeks; this is the operating calendar used in Part B. The catalog quotes the shorter total-hours ÷ 30 figure.

## A2. Rollout Phases

| Phase | Weeks | Work | Deliverables | Owner |
| --- | --- | --- | --- | --- |
| 0 — Approvals | 1–8 | Adopt catalog v3.2 after instructor review (Part C form); confirm state proprietary-school licensing and catalog filing requirements with the Louisiana Board of Regents (Proprietary Schools); set tuition, refund and enrollment-agreement terms per program; define clock-hour attendance audit method | Approved catalog v3.3 · licensing packet · enrollment agreement · tuition schedule | Owner / Director |
| 1 — Content build | 1–16 | Merge IPDG manuals (v1, v2, PPC-GRM) into MAN-IPDG with IPDG-401 practicum chapter; merge MAN-BUS + LDR per catalog Appendix A; author LSH M01–M10 lesson content; author 6 applied-capstone guides and 2 practicum logs; build evidence kits (10 activities, 10 micro-checks, 2 checkpoints, quiz) for every new or merged module | MAN-IPDG v3 · MAN-BUS v3 · MAN-LSH lessons · capstone guides · practicum logs · evidence kits | Lead instructor + curriculum writer |
| 2 — Systems | 4–16 | Load pathway → level → module structure into the LMS; clock-hour attendance tracking per module; ingest sources per catalog Section 11 rules; provision Owner-Operator Toolkit sanACAox accounts (booking/CRM, bookkeeping, payments) | LMS live · attendance reports · RAG index · toolkit accounts | Technology lead |
| 3 — Facilities & staffing | 6–20 | Fit out salon floor, training floor, cat room, business studio and personal-readiness space (catalog Section 9 equipment); hire/qualify instructors per A5; CPR/First Aid instructor certification; instructor onboarding on rubric, module flow and Part B syllabi | Facility checklist signed · instructor roSitter · certifications on file | Director |
| 4 — Pilot cohorts | 20–32 | Run PPS and CAT certificates (2 weeks each) and start one ACA cohort; collect rubric scores, attendance and capstone outcomes; fix content and pacing | Pilot report · revised pacing · catalog errata | Lead instructor |
| 5 — Full launch | 32+ | Open IPDG, PDT and PPC cohorts on rolling starts; publish annual calendar; begin employer/partner placements for practicum PPSes | Cohort calendar · partner MOUs · first diploma awards | Director |
| 6 — Continuous improvement | Quarterly | Review KPIs (A10); update source legend; re-ingest changed manuals; annual catalog edition | Quarterly review memo · annual catalog | Owner / Director |

## A3. Delivery Calendar by Program

| Program | Term 1 (100) | Term 2 (200) | Term 3 (300) | Term 4 (400) | Total | Sched. / PT weeks |
| --- | --- | --- | --- | --- | --- | --- |
| IPDG | 311 hr (11 wk) | 311 hr (11 wk) | 346 hr (12 wk) | 280 hr (10 wk) | 1,248 | 44 / 84 |
| PDT | 256 hr (9 wk) | 266 hr (9 wk) | 336 hr (12 wk) | 254 hr (9 wk) | 1,112 | 39 / 75 |
| ACA | 248 hr (9 wk) | 246 hr (9 wk) | 266 hr (9 wk) | 228 hr (8 wk) | 988 | 35 / 66 |
| PPS | 38 hr (2 wk) | 6 hr (1 day) | 6 hr (1 day) | 6 hr (1 day) | 56 | 2 / 4 |
| CAT | 40 hr (2 wk) | 6 hr (1 day) | 6 hr (1 day) | 6 hr (1 day) | 58 | 2 / 4 |
| PPC | 331 hr (12 wk) | 386 hr (13 wk) | 441 hr (15 wk) | 342 hr (12 wk) | 1,500 | 52 / 100 |

## A4. Weekly Schedule Template (full-time)

| Block | Mon | Tue | Wed | Thu | Fri |
| --- | --- | --- | --- | --- | --- |
| 08:00–12:00 | Technical lab | Technical lab | Technical lab | Technical lab | Practicum / open lab |
| 12:30–14:30 | Business module | Personal module | Business module | Business module | Applied capstone work |
| 14:30–15:30 | Micro-checks + AI workflow log | Micro-checks + AI workflow log | Checkpoint / quiz | Micro-checks + AI workflow log | Rubric review with instructor |
| Hours | 6 | 6 | 6 | 6 | 6 |

The technical / business split per week is set by the syllabus tables in Part B (Hours column). Where the technical share is below 12 hr/week, the morning block runs three days and business modules fill the remainder.

## A5. Staffing Model

| Role | Covers | Ratio / load | Minimum qualifications | FTE at full launch |
| --- | --- | --- | --- | --- |
| Grooming instructor | IPDG technical, PPC grooming modules, CAT | 1 : 6 on the salon floor | Certified/maSitter groomer, 5+ yr salon experience, CPR/First Aid instructor | 2 |
| Training instructor | PDT technical, PPC training modules | 1 : 8 on the training floor | Certified professional dog trainer (CPDT or equivalent), 5+ yr | 1 |
| Animal care instructor | ACA, PPS, handling and sanitation modules | 1 : 8 | Veterinary technician or senior bather/kennel lead | 1 |
| Business instructor | BUS, MKT, FIN, LEG families; applied capstones | 1 : 15 classroom | Small-business owner or MBA/CPA/JD as relevant; grooming or training industry familiarity | 2 |
| Personal readiness coach | LSH, PER families; learner support | 1 : 15; weekly 1:1 check-ins in Term 1 | Counseling, social work or coaching credential | 1 |
| Technology & AI lead | TEC family; LMS; RAG ingestion | Shared | LMS administration, data privacy basics, AI tooling | 0.5 |
| Director / registrar | Compliance, clock-hour audit, enrollment, records | — | Proprietary-school administration experience | 1 |

## A6. Facilities Readiness

| Space | Used by | Minimum standard | Ready by |
| --- | --- | --- | --- |
| Salon floor | IPDG, CAT, PPC, ACA | 6 grooming stations, 3 tubs, drying area, sanitation station, cat room separated from dogs | Phase 3 |
| Training floor | PDT, PPC | Indoor ring, outdoor secure yard, equipment storage | Phase 3 |
| Business studio | All pathways | Classroom for 15, projector, laptops/tablets, booking/CRM and bookkeeping sanACAoxes, printer for waivers and price menus | Phase 2 |
| Personal readiness space | All pathways | Private 1:1 room, quiet study area, resource board (housing, transport, benefits, health) | Phase 3 |
| Practicum PPSes | IPDG, PDT, PPC | Owned salon/training floor plus partner PPSes under MOU with supervision log | Phase 5 |

## A7. Content Build Backlog

| Item | Source manuals / inputs | Modules | Phase |
| --- | --- | --- | --- |
| MAN-IPDG v3 (merged grooming manual) | IPDG v1, IPDG102 v2, PPC-GRM manuals; REF-GRM-01…04 | IPDG-101…402; PPC-104…106, 301…306 | 1 |
| IPDG-401 / PPC-409 practicum logs | MAN-IPDG; salon SOPs | IPDG-401, PPC-409 | 1 |
| MAN-BUS v3 (merged BUS + LDR) | MAN-BUS, legacy LDR manual; catalog Appendix A | BUS-101…406 | 1 |
| MAN-LSH lesson content (M01–M10) | REF-LSH-01…04, REF-PER-05/06 | LSH-101…405 | 1 |
| Applied capstone guides ×6 | MAN-BUS + trade manual; REF-BIZ-02/04/05, REF-FIN-03, REF-MKT-07 | GRM-BIZ, TRN-BIZ, ACA-BIZ, PPS-BIZ, CAT-BIZ, PPC-BIZ | 1 |
| Evidence kits for new/merged modules | Module M01–M10 sequences (catalog Sections 3–8) | All NEW and merged modules | 1 |
| Owner-Operator Toolkit templates | REF-FIN-03, REF-LEG-05, MAN-LEG | FIN-101…105, LEG-101…103, BUS-205 | 2 |
| Prompt library + verification checklist | MAN-TEC; REF-AI-03/06/15 | TEC-105, LSH-203, all AI-requirement items | 2 |
| Syllabus packets per cohort | Part B tables + cohort dates | All pathways | 3 |

## A8. Assessment & Clock-Hour Controls

| Control | Method | Frequency | Record |
| --- | --- | --- | --- |
| Attendance = clock hours | Sign-in per scheduled block; instructor attestation; LMS timestamp for online theory | Every block | Attendance ledger per learner per module |
| Module evidence | 10 activities, 10 micro-checks, 2 checkpoints, final quiz, capstone artifact | Per module | LMS gradebook + artifact folder |
| Safety-critical gates | Instructor sign-off before live-animal work; CPR/First Aid checkoff before practicum | Before first live service; before practicum | Signed checklist |
| Practicum minimums | IPDG-401: 16 supervised live-client grooms; PPC-409: multi-service log; PDT-401/PPC-408: private class delivered | Term 4 | Practicum log with supervisor signature |
| Rubric scoring | All animal-care rows plus business & personal rows at Competent | Checkpoints and capstone | Rubric sheet per learner |
| Applied capstone review | Instructor + owner panel; launch plan, price menu, licensing/insurance worksheet, 90-day calendar | End of program | Panel score sheet |
| Credential issue | All modules , hours met, rubric Competent, capstone passed | End of program | Transcript with clock hours by module |

## A9. AI / RAG Ingestion Steps

| Step | Action | Output |
| --- | --- | --- |
| 1 | Tag every chunk with source ID, pathway codes, module codes and safety flag from catalog Section 11 | Tagged chunks |
| 2 | Chunk core manuals by module → M01–M10 → clock-hour block; reference texts per their chunk strategy | Indexed corpus |
| 3 | Retrieve by pathway then module code; core manuals outrank references; supplementary last | Retrieval policy |
| 4 | Safety-flagged chunks (CPR, medical, tax, legal) require instructor verification before use with learners | Verification queue |
| 5 | Re-ingest MAN-IPDG, MAN-BUS and MAN-LSH after Phase 1; retire legacy IPDG v1/v2, PPC-GRM and LDR chunks | Updated index |
| 6 | Quarterly: check every module still has at least one core source and one reference (catalog coverage table) | Coverage report |

## A10. Launch KPIs

| Metric | Target | Review |
| --- | --- | --- |
| Module completion within term | ≥ 90% of enrolled learners | End of each term |
| Clock-hour attendance | ≥ 95% of scheduled hours per learner | Weekly |
| Rubric Competent on all rows | 100% of graduates | Capstone |
| Applied capstone passed first attempt | ≥ 80% | End of program |
| Practicum minimums met | 100% before credential issue | Term 4 |
| Graduates operating or employed within 6 months | ≥ 75%; owner-operators tracked separately | Semi-annual |
| Source coverage | Every module has ≥ 1 core and ≥ 1 reference source | Quarterly |

# Part B — Pathway Syllabi

| Syllabus | Program | Weeks | Modules | Clock hours |
| --- | --- | --- | --- | --- |
| B1 | Professional Dog Groomer IIPDG | 44 | 157 | 1,248 |
| B2 | Professional Dog Trainer (PDT) | 39 | 155 | 1,112 |
| B3 | Animal Care Assistant ACA | 35 | 150 | 988 |
| B4 | Professional Pet PPSitter PPS | 2 | 11 | 56 |
| B5 | Professional Cat Groomer (CAT) | 2 | 11 | 58 |
| B6 | Professional Pet Care & Business Ownership PPC | 52 | 172 | 1,500 |

Each syllabus follows the same structure: Course Information → Term Outline → Week-by-Week Schedule → Assessment Calendar → Required & Reference Texts. Module content (M01–M10) and evidence are in the catalog, Sections 3–8.

# B1. Syllabus —  Professional Dog Groomer IIPDG

## Course Information

| Program / code | Professional Dog Groomer IIPDG |
| --- | --- |
| Credential | Professional Dog Groomer Diploma (Diploma) |
| Clock hours | 1,248 total — technical 360 · business & personal 864 · applied capstone 24 |
| Scheduled length | 44 weeks full-time (30 hr/wk, Mon–Fri 08:00–15:30) · ≈ 84 weeks part-time (15 hr/wk, evenings/Saturday) |
| Program objective | Identify dog stages and understand dog life · Recognize breeds · Recognize grooming tools · Identify workplace safety · Provide basic and advanced grooming techniques · Provide handling and pet care · Understand sanitation · supervised live-client salon services · Build, price, market and operate a grooming business · Manage personal readiness, finances and well-being as an owner · Provide CPR and first aid. |
| Admission | Age 18+ (17 with guardian consent); high-school diploma, GED or ability-to-benefit assessment; physical ability to lift 40 lb and stand for lab blocks; signed animal-handling risk acknowledgement |
| Instructional team | Grooming instructor (technical, GRM-BIZ panel) · Business instructor · Personal readiness coach · Technology & AI lead |
| Required materials | Professional Dog Groomer Tools kit (catalog Section 9) · Owner-Operator Toolkit sanACAox accounts · laptop or tablet |
| Required texts | 8 core manuals; 68 reference and supplementary texts (Required & Reference Texts below) |
| Attendance policy | Clock hours are earned only for attended blocks. Minimum 95% attendance per term; missed lab hours are made up in Friday open lab within the same term. Below 90% at any checkpoint triggers a coach meeting and written plan. |
| Grading | Module: 10 activities + 10 micro-checks , 2 checkpoints and final quiz at ≥ 80%, capstone artifact accepted. Program: Competency Rubric at Competent on every row (catalog Section 9); safety-critical rows are pass/fail. |
| Safety gates | IPDG-103, IPDG-302, IPDG-402 signed off before live-animal work; CPR/First Aid before practicum |
| Completion requirements | All 157 modules · 1,248 clock hours recorded · rubric Competent · GRM-BIZ capstone passed by panel · practicum log signed |
| Stacks into | PPC Advanced Diploma (all technical and business & personal modules credited) |

## Term Outline

| Term | Technical modules | Business & personal modules | Applied | Hrs: tech / biz / applied | Term hours |
| --- | --- | --- | --- | --- | --- |
| Term 1 — Foundation | IPDG-101, IPDG-102, IPDG-103, IPDG-104 | 36 modules: LSH 101–105, PER 101–105, BUS 101–106, MKT 101–105, TEC 101–105, FIN 101–105, LEG 101–105 | — | 95 / 216 / 0 | 311 (≈11 wk) |
| Term 2 — Core Skill | IPDG-201, IPDG-202, IPDG-203, IPDG-204 | 36 modules: LSH 201–205, PER 201–205, BUS 201–206, MKT 201–205, TEC 201–205, FIN 201–205, LEG 201–205 | — | 95 / 216 / 0 | 311 (≈11 wk) |
| Term 3 — Advanced Skill | IPDG-301, IPDG-302 | 36 modules: LSH 301–305, PER 301–305, BUS 301–306, MKT 301–305, TEC 301–305, FIN 301–305, LEG 301–305 | — | 130 / 216 / 0 | 346 (≈12 wk) |
| Term 4 — Capstone | IPDG-401, IPDG-402 | 36 modules: LSH 401–405, PER 401–405, BUS 401–406, MKT 401–405, TEC 401–405, FIN 401–405, LEG 401–405 | GRM-BIZ | 40 / 216 / 24 | 280 (≈10 wk) |
| Program total |  |  |  | 360 / 864 / 24 | 1,248 (≈42 wk) |

## Week-by-Week Schedule

Hours column = technical / business & personal clock hours per week. "(cont.)" = module continues into the next week. Quizzes are taken in the week a module closes; level checkpoints and rubric reviews close each term.

| Week | Term | Technical modules | Business & personal modules | Hrs | Assessments this week |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | T1 Foundation | IPDG‑101 (cont.) | LSH‑101, LSH‑102, LSH‑103, LSH‑104 (cont.) | 9 / 20 | Quizzes: LSH‑101, LSH‑102, LSH‑103 |
| Wk 2 | T1 Foundation | IPDG‑101 (cont.) | LSH‑104, LSH‑105, PER‑101, PER‑102 (cont.) | 9 / 20 | Quizzes: LSH‑104, LSH‑105, PER‑101 |
| Wk 3 | T1 Foundation | IPDG‑101, IPDG‑102 (cont.) | PER‑102, PER‑103, PER‑104, PER‑105 (cont.) | 9 / 20 | Quizzes: IPDG‑101, PER‑102, PER‑103, PER‑104 |
| Wk 4 | T1 Foundation | IPDG‑102 (cont.) | PER‑105, BUS‑101, BUS‑102, BUS‑103, BUS‑104 (cont.) | 9 / 20 | Quizzes: PER‑105, BUS‑101, BUS‑102, BUS‑103 |
| Wk 5 | T1 Foundation | IPDG‑102 (cont.) | BUS‑104, BUS‑105, BUS‑106, MKT‑101 (cont.) | 9 / 20 | Quizzes: BUS‑104, BUS‑105, BUS‑106 |
| Wk 6 | T1 Foundation | IPDG‑102, IPDG‑103 (cont.) | MKT‑101, MKT‑102, MKT‑103, MKT‑104 (cont.) | 9 / 20 | Quizzes: IPDG‑102, MKT‑101, MKT‑102, MKT‑103 |
| Wk 7 | T1 Foundation | IPDG‑103 (cont.) | MKT‑104, MKT‑105, TEC‑101, TEC‑102 (cont.) | 9 / 20 | Quizzes: MKT‑104, MKT‑105, TEC‑101 |
| Wk 8 | T1 Foundation | IPDG‑103 (cont.) | TEC‑102, TEC‑103, TEC‑104, TEC‑105, FIN‑101 (cont.) | 9 / 20 | Quizzes: TEC‑102, TEC‑103, TEC‑104, TEC‑105 |
| Wk 9 | T1 Foundation | IPDG‑103, IPDG‑104 (cont.) | FIN‑101, FIN‑102, FIN‑103, FIN‑104 (cont.) | 9 / 20 | Quizzes: IPDG‑103, FIN‑101, FIN‑102, FIN‑103 |
| Wk 10 | T1 Foundation | IPDG‑104 (cont.) | FIN‑104, FIN‑105, LEG‑101, LEG‑102 (cont.) | 9 / 20 | Quizzes: FIN‑104, FIN‑105, LEG‑101 |
| Wk 11 | T1 Foundation | IPDG‑104 | LEG‑102, LEG‑103, LEG‑104, LEG‑105 | 9 / 20 | Quizzes: IPDG‑104, LEG‑102, LEG‑103, LEG‑104, LEG‑105 · Level checkpoint · rubric review |
| Wk 12 | T2 Core Skill | IPDG‑201 (cont.) | LSH‑201, LSH‑202, LSH‑203, LSH‑204 (cont.) | 9 / 20 | Quizzes: LSH‑201, LSH‑202, LSH‑203 |
| Wk 13 | T2 Core Skill | IPDG‑201 (cont.) | LSH‑204, LSH‑205, PER‑201, PER‑202 (cont.) | 9 / 20 | Quizzes: LSH‑204, LSH‑205, PER‑201 |
| Wk 14 | T2 Core Skill | IPDG‑201, IPDG‑202 (cont.) | PER‑202, PER‑203, PER‑204, PER‑205 (cont.) | 9 / 20 | Quizzes: IPDG‑201, PER‑202, PER‑203, PER‑204 |
| Wk 15 | T2 Core Skill | IPDG‑202 (cont.) | PER‑205, BUS‑201, BUS‑202, BUS‑203, BUS‑204 (cont.) | 9 / 20 | Quizzes: PER‑205, BUS‑201, BUS‑202, BUS‑203 |
| Wk 16 | T2 Core Skill | IPDG‑202 (cont.) | BUS‑204, BUS‑205, BUS‑206, MKT‑201 (cont.) | 9 / 20 | Quizzes: BUS‑204, BUS‑205, BUS‑206 |
| Wk 17 | T2 Core Skill | IPDG‑202, IPDG‑203 (cont.) | MKT‑201, MKT‑202, MKT‑203, MKT‑204 (cont.) | 9 / 20 | Quizzes: IPDG‑202, MKT‑201, MKT‑202, MKT‑203 |
| Wk 18 | T2 Core Skill | IPDG‑203 (cont.) | MKT‑204, MKT‑205, TEC‑201, TEC‑202 (cont.) | 9 / 20 | Quizzes: MKT‑204, MKT‑205, TEC‑201 |
| Wk 19 | T2 Core Skill | IPDG‑203 (cont.) | TEC‑202, TEC‑203, TEC‑204, TEC‑205, FIN‑201 (cont.) | 9 / 20 | Quizzes: TEC‑202, TEC‑203, TEC‑204, TEC‑205 |
| Wk 20 | T2 Core Skill | IPDG‑203, IPDG‑204 (cont.) | FIN‑201, FIN‑202, FIN‑203, FIN‑204 (cont.) | 9 / 20 | Quizzes: IPDG‑203, FIN‑201, FIN‑202, FIN‑203 |
| Wk 21 | T2 Core Skill | IPDG‑204 (cont.) | FIN‑204, FIN‑205, LEG‑201, LEG‑202 (cont.) | 9 / 20 | Quizzes: FIN‑204, FIN‑205, LEG‑201 |
| Wk 22 | T2 Core Skill | IPDG‑204 | LEG‑202, LEG‑203, LEG‑204, LEG‑205 | 9 / 20 | Quizzes: IPDG‑204, LEG‑202, LEG‑203, LEG‑204, LEG‑205 · Level checkpoint · rubric review |
| Wk 23 | T3 Advanced Skill | IPDG‑301 (cont.) | LSH‑301, LSH‑302, LSH‑303 | 11 / 18 | Quizzes: LSH‑301, LSH‑302, LSH‑303 |
| Wk 24 | T3 Advanced Skill | IPDG‑301 (cont.) | LSH‑304, LSH‑305, PER‑301 | 11 / 18 | Quizzes: LSH‑304, LSH‑305, PER‑301 |
| Wk 25 | T3 Advanced Skill | IPDG‑301 (cont.) | PER‑302, PER‑303, PER‑304 | 11 / 18 | Quizzes: PER‑302, PER‑303, PER‑304 |
| Wk 26 | T3 Advanced Skill | IPDG‑301 (cont.) | PER‑305, BUS‑301, BUS‑302 | 11 / 18 | Quizzes: PER‑305, BUS‑301, BUS‑302 |
| Wk 27 | T3 Advanced Skill | IPDG‑301 (cont.) | BUS‑303, BUS‑304, BUS‑305 | 11 / 18 | Quizzes: BUS‑303, BUS‑304, BUS‑305 |
| Wk 28 | T3 Advanced Skill | IPDG‑301 (cont.) | BUS‑306, MKT‑301, MKT‑302 | 11 / 18 | Quizzes: BUS‑306, MKT‑301, MKT‑302 |
| Wk 29 | T3 Advanced Skill | IPDG‑301 (cont.) | MKT‑303, MKT‑304, MKT‑305 | 11 / 18 | Quizzes: MKT‑303, MKT‑304, MKT‑305 |
| Wk 30 | T3 Advanced Skill | IPDG‑301 (cont.) | TEC‑301, TEC‑302, TEC‑303 | 11 / 18 | Quizzes: TEC‑301, TEC‑302, TEC‑303 |
| Wk 31 | T3 Advanced Skill | IPDG‑301 (cont.) | TEC‑304, TEC‑305, FIN‑301 | 11 / 18 | Quizzes: TEC‑304, TEC‑305, FIN‑301 |
| Wk 32 | T3 Advanced Skill | IPDG‑301 (cont.) | FIN‑302, FIN‑303, FIN‑304 | 11 / 18 | Quizzes: FIN‑302, FIN‑303, FIN‑304 |
| Wk 33 | T3 Advanced Skill | IPDG‑301, IPDG‑302 (cont.) | FIN‑305, LEG‑301, LEG‑302 | 11 / 18 | Quizzes: IPDG‑301, FIN‑305, LEG‑301, LEG‑302 |
| Wk 34 | T3 Advanced Skill | IPDG‑302 | LEG‑303, LEG‑304, LEG‑305 | 11 / 18 | Quizzes: IPDG‑302, LEG‑303, LEG‑304, LEG‑305 · Level checkpoint · rubric review |
| Wk 35 | T4 Capstone | IPDG‑401 (cont.) | LSH‑401, LSH‑402, LSH‑403, LSH‑404 | 4 / 24 | Quizzes: LSH‑401, LSH‑402, LSH‑403, LSH‑404 |
| Wk 36 | T4 Capstone | IPDG‑401 (cont.) | LSH‑405, PER‑401, PER‑402, PER‑403 | 4 / 24 | Quizzes: LSH‑405, PER‑401, PER‑402, PER‑403 |
| Wk 37 | T4 Capstone | IPDG‑401 (cont.) | PER‑404, PER‑405, BUS‑401, BUS‑402 | 4 / 24 | Quizzes: PER‑404, PER‑405, BUS‑401, BUS‑402 |
| Wk 38 | T4 Capstone | IPDG‑401 (cont.) | BUS‑403, BUS‑404, BUS‑405, BUS‑406 | 4 / 24 | Quizzes: BUS‑403, BUS‑404, BUS‑405, BUS‑406 |
| Wk 39 | T4 Capstone | IPDG‑401 (cont.) | MKT‑401, MKT‑402, MKT‑403, MKT‑404 | 4 / 24 | Quizzes: MKT‑401, MKT‑402, MKT‑403, MKT‑404 |
| Wk 40 | T4 Capstone | IPDG‑401 (cont.) | MKT‑405, TEC‑401, TEC‑402, TEC‑403 | 4 / 24 | Quizzes: MKT‑405, TEC‑401, TEC‑402, TEC‑403 |
| Wk 41 | T4 Capstone | IPDG‑401 (cont.) | TEC‑404, TEC‑405, FIN‑401, FIN‑402 | 4 / 24 | Quizzes: TEC‑404, TEC‑405, FIN‑401, FIN‑402 |
| Wk 42 | T4 Capstone | IPDG‑401 | FIN‑403, FIN‑404, FIN‑405, LEG‑401 | 4 / 24 | Quizzes: IPDG‑401, FIN‑403, FIN‑404, FIN‑405, LEG‑401 |
| Wk 43 | T4 Capstone | IPDG‑402 (cont.) | LEG‑402, LEG‑403, LEG‑404, LEG‑405 | 4 / 24 | Quizzes: LEG‑402, LEG‑403, LEG‑404, LEG‑405 |
| Wk 44 | T4 Capstone | IPDG‑402 | GRM‑BIZ | 4 / 24 | Quizzes: IPDG‑402, GRM‑BIZ · Level checkpoint · rubric review · Capstone panel · practicum sign-off |

## Assessment Calendar

| Point | When | Instrument | Pass standard |
| --- | --- | --- | --- |
| Module quizzes and checkpoints | Week each module closes (see schedule) | Final quiz + 2 checkpoints + capstone artifact | ≥ 80%; artifact accepted |
| Level checkpoint 1 | Last week of Term 1 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 2 | Last week of Term 2 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 3 | Last week of Term 3 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 4 | Last week of Term 4 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Safety-critical sign-off | Before first live-animal service | Instructor checklist (handling, sanitation, CPR/First Aid) | Pass/fail |
| Practicum | Final term | Supervised practicum log | Minimums met and supervisor signature |
| Applied business capstone | Final week — GRM-BIZ | Instructor + owner panel | Launch plan, price menu, licensing/insurance worksheet, 90-day calendar accepted |

## Required & Reference Texts

| ID | Title | Author / publisher | Type |
| --- | --- | --- | --- |
| MAN‑IPDG | Professional Dog Groomer (merged: v1 200 hr + v2 300 hr + PPC grooming track) | Leashed program manual | Core manual |
| MAN‑LSH | Life Skills & Personal Readiness | Leashed program manual | Core manual |
| MAN‑BUS | Business & Leadership: Ownership, Operations & Expansion (merged BUS + LDR) | Leashed program manual | Core manual |
| MAN‑PER | Personal MaSittery & Lifelong Growth | Leashed program manual | Core manual |
| MAN‑MKT | Marketing, Branding & SEO MaSittery | Leashed program manual | Core manual |
| MAN‑TEC | AI & Technology Systems | Leashed program manual | Core manual |
| MAN‑FIN | Financial MaSittery, Bookkeeping & Tax Strategy | Leashed program manual | Core manual |
| MAN‑LEG | Legal, Risk, Compliance & Ethical Governance | Leashed program manual | Core manual |
| REF‑GRM‑01 | Dog Grooming for Beginners | Jorge Bendersky | Reference text · Book |
| REF‑GRM‑02 | Grooming Manual for Dog and Cat | — | Reference text · DOCX manuscript |
| REF‑GRM‑03 | The Everything Dog Grooming Book | — | Reference text · DOCX manuscript |
| REF‑BEH‑01 | HanACAook of Applied Dog Behavior and Training, Vol. 3 | Steven R. Lindsay | Reference text · Book |
| REF‑MED‑01 | Small Animal Critical Care Medicine | — | Reference text · Book |
| REF‑AI‑01 | AI for Animals: Revolutionizing Veterinary Care | Amelia Hawkins | Supplementary text · Book |
| REF‑ANI‑01 | Beastly: The 40,000-Year Story of Animals and Us | — | Supplementary text · Book |
| REF‑CARE‑01 | Knack Dog Care and Training | — | Reference text · Book |
| REF‑BIZ‑01 | Business Cycles | Francis X. Diebold | Supplementary text · Book |
| REF‑BIZ‑02 | Building a Successful Business | Dominik Mikulaschek | Reference text · Book |
| REF‑BIZ‑03 | The Disruptors | Sally Percy | Supplementary text · Book |
| REF‑BIZ‑04 | Go It Alone! | Bruce Judson | Reference text · Book |
| REF‑BIZ‑05 | The Successful Entrepreneur Playbook | Paul H. Woodruff | Reference text · Book |
| REF‑BIZ‑06 | 4-Hour Work Day | — | Supplementary text · Book |
| REF‑BIZ‑07 | The Business Bible | — | Reference text · Book |
| REF‑BIZ‑08 | Poverty Traps | Samuel Bowles | Supplementary text · Book |
| REF‑LDR‑01 | Leadership Presence | Belle Linda Halpern | Reference text · Book |
| REF‑LDR‑02 | Leadership and Ethics | Jacqueline Boaks | Reference text · Book |
| REF‑MKT‑01 | Multi-Channel Marketing, Branding and Retail Design | — | Reference text · Book |
| REF‑MKT‑02 | Marketing is not Rocket Science | — | Reference text · Book |
| REF‑MKT‑03 | Unconscious Branding | Douglas Van Praet | Supplementary text · Book |
| REF‑MKT‑04 | Content Branding Solutions for Entrepreneur Strategic Content Marketing | Peter Lucking | Reference text · Book |
| REF‑MKT‑05 | Branding: What You Need to Know About Building a Personal Brand… | — | Reference text · Book |
| REF‑MKT‑06 | Business Branding Guide | — | Reference text · Book |
| REF‑MKT‑07 | Salon Marketing | — | Reference text · Book |
| REF‑CX‑01 | Customer Service in Health Care | Kristin Baird | Reference text · Book |
| REF‑CX‑02 | Can Your Customer Service Do This? | — | Reference text · Book |
| REF‑CX‑03 | Crushing the Competition with Service | — | Reference text · Book |
| REF‑CX‑04 | Customer Service Is Just Foreplay | Jason D. Cass | Supplementary text · Book |
| REF‑FIN‑01 | J.K. Lasser's Small Business Taxes 2025 | — | Reference text · Book |
| REF‑FIN‑02 | Tax Accounting: A Guide for Small Business Owners | — | Reference text · Book |
| REF‑FIN‑03 | Small Time Operator | — | Reference text · Book |
| REF‑FIN‑04 | 475 Tax Deductions for All Small Businesses | — | Reference text · Book |
| REF‑LEG‑01 | Cybersecurity: Ethics, Legal, Risks | Ishaani Priyadarshini | Reference text · Book |
| REF‑LEG‑02 | The Tax and Legal Playbook | Mark J. Kohler | Reference text · Book |
| REF‑LEG‑03 | Reimagining Fairness: Equity, Cultural DiverPPSy, and Inclusion Competency Approach | — | Reference text · Book |
| REF‑LEG‑04 | PCI Compliance | Dr. Branden R. Williams | Reference text · Book |
| REF‑LEG‑05 | The Guide to OSHA Compliance | Robert D. Peterson | Reference text · Book |
| REF‑LEG‑06 | Security-First Compliance for Small Businesses | — | Reference text · Book |
| REF‑LEG‑07 | Transfer Pricing: Rules, Compliance and Controversy | — | Supplementary text · Book |
| REF‑LEG‑08 | Stop Harming Customers: A Compliance Manifesto | David Silverman | Reference text · Book |
| REF‑LEG‑09 | Tools of Effective Compliance | Thomas Schneider | Reference text · Book |
| REF‑LSH‑01 | Teaching life skills in intermediate phase | — | Reference text · Book |
| REF‑LSH‑02 | Stuff Students Should Know: Learn Essential Life Skills | — | Reference text · Book |
| REF‑LSH‑03 | 10 Proven Ways to Relieve Stress Now | — | Supplementary text · Book |
| REF‑LSH‑04 | Personal Finance | — | Reference text · Book |
| REF‑PER‑01 | The Personal MBA | Josh Kaufman | Reference text · Book |
| REF‑PER‑02 | Self-Talk Your Way to Success | Kam Knight | Reference text · Book |
| REF‑PER‑03 | Are You Ready to Succeed? | — | Reference text · Book |
| REF‑PER‑04 | Trigger High Performance | — | Reference text · Book |
| REF‑PER‑05 | Rebuilding Relationships in Recovery | — | Reference text · Book |
| REF‑PER‑06 | Trust Yourself: Stop Overthinking and Channel Your Emotions for Success at Work | — | Reference text · Book |
| REF‑AI‑02 | LinkedIn Personal Branding and Marketing | — | Reference text · Book |
| REF‑AI‑03 | The Marketing Mindset: 100 ChatGPT Prompts | — | Reference text · Book |
| REF‑AI‑04 | Enterprise AI | Shazia Sadiq | Reference text · Book |
| REF‑AI‑05 | AI In Finance | Krishan Arora | Reference text · Book |
| REF‑AI‑06 | AI Timekeeper | Robert Breeser | Reference text · Book |
| REF‑AI‑07 | AI Profit Hacks | — | Reference text · Book |
| REF‑AI‑08 | AI Startup Strategy | Adhiguna Mahendra | Reference text · Book |
| REF‑AI‑09 | AI and the Boardroom | Rohan Sharma | Reference text · Book |
| REF‑AI‑10 | Foundations of Agentic AI for Retail | — | Reference text · Book |
| REF‑AI‑11 | Retail 4.0: How AI is Shaping the Future of Shopping | — | Supplementary text · Book |
| REF‑AI‑12 | AI-Powered Accounting with Excel and Power BI | — | Reference text · Book |
| REF‑AI‑13 | The AI Revolution in Customer Service | — | Reference text · Book |
| REF‑AI‑14 | Natural Language Processing with Python: Building your Own Customer Service ChatBot | — | Reference text · Book |
| REF‑AI‑15 | Teaching and Learning in the Age of Generative AI | — | Reference text · Book |

# B2. Syllabus — Professional Dog Trainer (PDT)

## Course Information

| Program / code | Professional Dog Trainer (PDT) |
| --- | --- |
| Credential | Professional Dog Trainer Diploma (Diploma) |
| Clock hours | 1,112 total — technical 224 · business & personal 864 · applied capstone 24 |
| Scheduled length | 39 weeks full-time (30 hr/wk, Mon–Fri 08:00–15:30) · ≈ 75 weeks part-time (15 hr/wk, evenings/Saturday) |
| Program objective | Recognize/search dog history · Offer guidance to new owners · Follow vaccination & ADA guides · Identify 10 most important AKC breeds · Recognize training equipment · Recognize personalities & behavior problems · Choose effective solutions · Train basic obedience · Train advanced obedience · Use in-motion commands, verbal & hand signals · Make corrections · Design private classes · Build, price, market and operate a training business · Manage personal readiness, finances and well-being as an owner · Understand continuous education · Provide CPR and first aid. |
| Admission | Age 18+ (17 with guardian consent); high-school diploma, GED or ability-to-benefit assessment; physical ability to lift 40 lb and stand for lab blocks; signed animal-handling risk acknowledgement |
| Instructional team | Training instructor (technical, TRN-BIZ panel) · Business instructor · Personal readiness coach · Technology & AI lead |
| Required materials | Professional Dog Trainer Tools kit (catalog Section 9) · Owner-Operator Toolkit sanACAox accounts · laptop or tablet |
| Required texts | 8 core manuals; 65 reference and supplementary texts (Required & Reference Texts below) |
| Attendance policy | Clock hours are earned only for attended blocks. Minimum 95% attendance per term; missed lab hours are made up in Friday open lab within the same term. Below 90% at any checkpoint triggers a coach meeting and written plan. |
| Grading | Module: 10 activities + 10 micro-checks , 2 checkpoints and final quiz at ≥ 80%, capstone artifact accepted. Program: Competency Rubric at Competent on every row (catalog Section 9); safety-critical rows are pass/fail. |
| Safety gates | PDT-201, PDT-402 signed off before live-animal work; CPR/First Aid before practicum |
| Completion requirements | All 155 modules · 1,112 clock hours recorded · rubric Competent · TRN-BIZ capstone passed by panel · practicum log signed |
| Stacks into | PPC Advanced Diploma (all technical and business & personal modules credited) |

## Term Outline

| Term | Technical modules | Business & personal modules | Applied | Hrs: tech / biz / applied | Term hours |
| --- | --- | --- | --- | --- | --- |
| Term 1 — Foundation | PDT-101, PDT-102, PDT-103 | 36 modules: LSH 101–105, PER 101–105, BUS 101–106, MKT 101–105, TEC 101–105, FIN 101–105, LEG 101–105 | — | 40 / 216 / 0 | 256 (≈9 wk) |
| Term 2 — Core Skill | PDT-201, PDT-202 | 36 modules: LSH 201–205, PER 201–205, BUS 201–206, MKT 201–205, TEC 201–205, FIN 201–205, LEG 201–205 | — | 50 / 216 / 0 | 266 (≈9 wk) |
| Term 3 — Advanced Skill | PDT-301, PDT-302, PDT-303 | 36 modules: LSH 301–305, PER 301–305, BUS 301–306, MKT 301–305, TEC 301–305, FIN 301–305, LEG 301–305 | — | 120 / 216 / 0 | 336 (≈12 wk) |
| Term 4 — Capstone | PDT-401, PDT-402 | 36 modules: LSH 401–405, PER 401–405, BUS 401–406, MKT 401–405, TEC 401–405, FIN 401–405, LEG 401–405 | TRN-BIZ | 14 / 216 / 24 | 254 (≈9 wk) |
| Program total |  |  |  | 224 / 864 / 24 | 1,112 (≈38 wk) |

## Week-by-Week Schedule

Hours column = technical / business & personal clock hours per week. "(cont.)" = module continues into the next week. Quizzes are taken in the week a module closes; level checkpoints and rubric reviews close each term.

| Week | Term | Technical modules | Business & personal modules | Hrs | Assessments this week |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | T1 Foundation | PDT‑101 (cont.) | LSH‑101, LSH‑102, LSH‑103, LSH‑104 | 4 / 24 | Quizzes: LSH‑101, LSH‑102, LSH‑103, LSH‑104 |
| Wk 2 | T1 Foundation | PDT‑101 (cont.) | LSH‑105, PER‑101, PER‑102, PER‑103 | 4 / 24 | Quizzes: LSH‑105, PER‑101, PER‑102, PER‑103 |
| Wk 3 | T1 Foundation | PDT‑101, PDT‑102 (cont.) | PER‑104, PER‑105, BUS‑101, BUS‑102 | 4 / 24 | Quizzes: PDT‑101, PER‑104, PER‑105, BUS‑101, BUS‑102 |
| Wk 4 | T1 Foundation | PDT‑102 (cont.) | BUS‑103, BUS‑104, BUS‑105, BUS‑106 | 4 / 24 | Quizzes: BUS‑103, BUS‑104, BUS‑105, BUS‑106 |
| Wk 5 | T1 Foundation | PDT‑102 (cont.) | MKT‑101, MKT‑102, MKT‑103, MKT‑104 | 4 / 24 | Quizzes: MKT‑101, MKT‑102, MKT‑103, MKT‑104 |
| Wk 6 | T1 Foundation | PDT‑102 (cont.) | MKT‑105, TEC‑101, TEC‑102, TEC‑103 | 4 / 24 | Quizzes: MKT‑105, TEC‑101, TEC‑102, TEC‑103 |
| Wk 7 | T1 Foundation | PDT‑102, PDT‑103 (cont.) | TEC‑104, TEC‑105, FIN‑101, FIN‑102 | 4 / 24 | Quizzes: PDT‑102, TEC‑104, TEC‑105, FIN‑101, FIN‑102 |
| Wk 8 | T1 Foundation | PDT‑103 (cont.) | FIN‑103, FIN‑104, FIN‑105, LEG‑101 | 4 / 24 | Quizzes: FIN‑103, FIN‑104, FIN‑105, LEG‑101 |
| Wk 9 | T1 Foundation | PDT‑103 | LEG‑102, LEG‑103, LEG‑104, LEG‑105 | 4 / 24 | Quizzes: PDT‑103, LEG‑102, LEG‑103, LEG‑104, LEG‑105 · Level checkpoint · rubric review |
| Wk 10 | T2 Core Skill | PDT‑201 (cont.) | LSH‑201, LSH‑202, LSH‑203, LSH‑204 | 6 / 24 | Quizzes: LSH‑201, LSH‑202, LSH‑203, LSH‑204 |
| Wk 11 | T2 Core Skill | PDT‑201 (cont.) | LSH‑205, PER‑201, PER‑202, PER‑203 | 6 / 24 | Quizzes: LSH‑205, PER‑201, PER‑202, PER‑203 |
| Wk 12 | T2 Core Skill | PDT‑201 (cont.) | PER‑204, PER‑205, BUS‑201, BUS‑202 | 6 / 24 | Quizzes: PER‑204, PER‑205, BUS‑201, BUS‑202 |
| Wk 13 | T2 Core Skill | PDT‑201 (cont.) | BUS‑203, BUS‑204, BUS‑205, BUS‑206 | 6 / 24 | Quizzes: BUS‑203, BUS‑204, BUS‑205, BUS‑206 |
| Wk 14 | T2 Core Skill | PDT‑201, PDT‑202 (cont.) | MKT‑201, MKT‑202, MKT‑203, MKT‑204 | 6 / 24 | Quizzes: PDT‑201, MKT‑201, MKT‑202, MKT‑203, MKT‑204 |
| Wk 15 | T2 Core Skill | PDT‑202 (cont.) | MKT‑205, TEC‑201, TEC‑202, TEC‑203 | 6 / 24 | Quizzes: MKT‑205, TEC‑201, TEC‑202, TEC‑203 |
| Wk 16 | T2 Core Skill | PDT‑202 (cont.) | TEC‑204, TEC‑205, FIN‑201, FIN‑202 | 6 / 24 | Quizzes: TEC‑204, TEC‑205, FIN‑201, FIN‑202 |
| Wk 17 | T2 Core Skill | PDT‑202 (cont.) | FIN‑203, FIN‑204, FIN‑205, LEG‑201 | 6 / 24 | Quizzes: FIN‑203, FIN‑204, FIN‑205, LEG‑201 |
| Wk 18 | T2 Core Skill | PDT‑202 | LEG‑202, LEG‑203, LEG‑204, LEG‑205 | 6 / 24 | Quizzes: PDT‑202, LEG‑202, LEG‑203, LEG‑204, LEG‑205 · Level checkpoint · rubric review |
| Wk 19 | T3 Advanced Skill | PDT‑301 (cont.) | LSH‑301, LSH‑302, LSH‑303 | 10 / 18 | Quizzes: LSH‑301, LSH‑302, LSH‑303 |
| Wk 20 | T3 Advanced Skill | PDT‑301 (cont.) | LSH‑304, LSH‑305, PER‑301 | 10 / 18 | Quizzes: LSH‑304, LSH‑305, PER‑301 |
| Wk 21 | T3 Advanced Skill | PDT‑301 (cont.) | PER‑302, PER‑303, PER‑304 | 10 / 18 | Quizzes: PER‑302, PER‑303, PER‑304 |
| Wk 22 | T3 Advanced Skill | PDT‑301 | PER‑305, BUS‑301, BUS‑302 | 10 / 18 | Quizzes: PDT‑301, PER‑305, BUS‑301, BUS‑302 |
| Wk 23 | T3 Advanced Skill | PDT‑302 (cont.) | BUS‑303, BUS‑304, BUS‑305 | 10 / 18 | Quizzes: BUS‑303, BUS‑304, BUS‑305 |
| Wk 24 | T3 Advanced Skill | PDT‑302 (cont.) | BUS‑306, MKT‑301, MKT‑302 | 10 / 18 | Quizzes: BUS‑306, MKT‑301, MKT‑302 |
| Wk 25 | T3 Advanced Skill | PDT‑302 (cont.) | MKT‑303, MKT‑304, MKT‑305 | 10 / 18 | Quizzes: MKT‑303, MKT‑304, MKT‑305 |
| Wk 26 | T3 Advanced Skill | PDT‑302 | TEC‑301, TEC‑302, TEC‑303 | 10 / 18 | Quizzes: PDT‑302, TEC‑301, TEC‑302, TEC‑303 |
| Wk 27 | T3 Advanced Skill | PDT‑303 (cont.) | TEC‑304, TEC‑305, FIN‑301 | 10 / 18 | Quizzes: TEC‑304, TEC‑305, FIN‑301 |
| Wk 28 | T3 Advanced Skill | PDT‑303 (cont.) | FIN‑302, FIN‑303, FIN‑304 | 10 / 18 | Quizzes: FIN‑302, FIN‑303, FIN‑304 |
| Wk 29 | T3 Advanced Skill | PDT‑303 (cont.) | FIN‑305, LEG‑301, LEG‑302 | 10 / 18 | Quizzes: FIN‑305, LEG‑301, LEG‑302 |
| Wk 30 | T3 Advanced Skill | PDT‑303 | LEG‑303, LEG‑304, LEG‑305 | 10 / 18 | Quizzes: PDT‑303, LEG‑303, LEG‑304, LEG‑305 · Level checkpoint · rubric review |
| Wk 31 | T4 Capstone | PDT‑401 (cont.) | LSH‑401, LSH‑402, LSH‑403, LSH‑404, LSH‑405 (cont.) | 2 / 27 | Quizzes: LSH‑401, LSH‑402, LSH‑403, LSH‑404 |
| Wk 32 | T4 Capstone | PDT‑401 (cont.) | LSH‑405, PER‑401, PER‑402, PER‑403, PER‑404 (cont.) | 2 / 27 | Quizzes: LSH‑405, PER‑401, PER‑402, PER‑403 |
| Wk 33 | T4 Capstone | PDT‑401 (cont.) | PER‑404, PER‑405, BUS‑401, BUS‑402, BUS‑403, BUS‑404 (cont.) | 2 / 27 | Quizzes: PER‑404, PER‑405, BUS‑401, BUS‑402, BUS‑403 |
| Wk 34 | T4 Capstone | PDT‑401, PDT‑402 (cont.) | BUS‑404, BUS‑405, BUS‑406, MKT‑401, MKT‑402 (cont.) | 2 / 27 | Quizzes: PDT‑401, BUS‑404, BUS‑405, BUS‑406, MKT‑401 |
| Wk 35 | T4 Capstone | PDT‑402 (cont.) | MKT‑402, MKT‑403, MKT‑404, MKT‑405, TEC‑401, TEC‑402 (cont.) | 2 / 27 | Quizzes: MKT‑402, MKT‑403, MKT‑404, MKT‑405, TEC‑401 |
| Wk 36 | T4 Capstone | PDT‑402 (cont.) | TEC‑402, TEC‑403, TEC‑404, TEC‑405, FIN‑401 (cont.) | 2 / 27 | Quizzes: TEC‑402, TEC‑403, TEC‑404, TEC‑405 |
| Wk 37 | T4 Capstone | PDT‑402 (cont.) | FIN‑401, FIN‑402, FIN‑403, FIN‑404, FIN‑405, LEG‑401 (cont.) | 2 / 27 | Quizzes: FIN‑401, FIN‑402, FIN‑403, FIN‑404, FIN‑405 |
| Wk 38 | T4 Capstone | PDT‑402 (cont.) | LEG‑401, LEG‑402, LEG‑403, LEG‑404, LEG‑405 (cont.) | 2 / 27 | Quizzes: LEG‑401, LEG‑402, LEG‑403, LEG‑404 |
| Wk 39 | T4 Capstone | PDT‑402 | LEG‑405, TRN‑BIZ | 2 / 27 | Quizzes: PDT‑402, LEG‑405, TRN‑BIZ · Level checkpoint · rubric review · Capstone panel · practicum sign-off |

## Assessment Calendar

| Point | When | Instrument | Pass standard |
| --- | --- | --- | --- |
| Module quizzes and checkpoints | Week each module closes (see schedule) | Final quiz + 2 checkpoints + capstone artifact | ≥ 80%; artifact accepted |
| Level checkpoint 1 | Last week of Term 1 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 2 | Last week of Term 2 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 3 | Last week of Term 3 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 4 | Last week of Term 4 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Safety-critical sign-off | Before first live-animal service | Instructor checklist (handling, sanitation, CPR/First Aid) | Pass/fail |
| Practicum | Final term | Supervised practicum log | Minimums met and supervisor signature |
| Applied business capstone | Final week — TRN-BIZ | Instructor + owner panel | Launch plan, price menu, licensing/insurance worksheet, 90-day calendar accepted |

## Required & Reference Texts

| ID | Title | Author / publisher | Type |
| --- | --- | --- | --- |
| MAN‑PDT | Professional Dog Trainer | Leashed program manual | Core manual |
| MAN‑LSH | Life Skills & Personal Readiness | Leashed program manual | Core manual |
| MAN‑BUS | Business & Leadership: Ownership, Operations & Expansion (merged BUS + LDR) | Leashed program manual | Core manual |
| MAN‑PER | Personal MaSittery & Lifelong Growth | Leashed program manual | Core manual |
| MAN‑MKT | Marketing, Branding & SEO MaSittery | Leashed program manual | Core manual |
| MAN‑TEC | AI & Technology Systems | Leashed program manual | Core manual |
| MAN‑FIN | Financial MaSittery, Bookkeeping & Tax Strategy | Leashed program manual | Core manual |
| MAN‑LEG | Legal, Risk, Compliance & Ethical Governance | Leashed program manual | Core manual |
| REF‑BEH‑01 | HanACAook of Applied Dog Behavior and Training, Vol. 3 | Steven R. Lindsay | Reference text · Book |
| REF‑TRN‑01 | Nate Schoemer's Dog Training Manual | — | Reference text · Book |
| REF‑HLTH‑01 | National Geographic Guide to Pet Health, Behavior, and Happiness | — | Reference text · Book |
| REF‑MED‑01 | Small Animal Critical Care Medicine | — | Reference text · Book |
| REF‑AI‑01 | AI for Animals: Revolutionizing Veterinary Care | Amelia Hawkins | Supplementary text · Book |
| REF‑ANI‑01 | Beastly: The 40,000-Year Story of Animals and Us | — | Supplementary text · Book |
| REF‑CARE‑01 | Knack Dog Care and Training | — | Reference text · Book |
| REF‑BIZ‑01 | Business Cycles | Francis X. Diebold | Supplementary text · Book |
| REF‑BIZ‑02 | Building a Successful Business | Dominik Mikulaschek | Reference text · Book |
| REF‑BIZ‑03 | The Disruptors | Sally Percy | Supplementary text · Book |
| REF‑BIZ‑04 | Go It Alone! | Bruce Judson | Reference text · Book |
| REF‑BIZ‑05 | The Successful Entrepreneur Playbook | Paul H. Woodruff | Reference text · Book |
| REF‑BIZ‑06 | 4-Hour Work Day | — | Supplementary text · Book |
| REF‑BIZ‑07 | The Business Bible | — | Reference text · Book |
| REF‑BIZ‑08 | Poverty Traps | Samuel Bowles | Supplementary text · Book |
| REF‑LDR‑01 | Leadership Presence | Belle Linda Halpern | Reference text · Book |
| REF‑LDR‑02 | Leadership and Ethics | Jacqueline Boaks | Reference text · Book |
| REF‑MKT‑01 | Multi-Channel Marketing, Branding and Retail Design | — | Reference text · Book |
| REF‑MKT‑02 | Marketing is not Rocket Science | — | Reference text · Book |
| REF‑MKT‑03 | Unconscious Branding | Douglas Van Praet | Supplementary text · Book |
| REF‑MKT‑04 | Content Branding Solutions for Entrepreneur Strategic Content Marketing | Peter Lucking | Reference text · Book |
| REF‑MKT‑05 | Branding: What You Need to Know About Building a Personal Brand… | — | Reference text · Book |
| REF‑MKT‑06 | Business Branding Guide | — | Reference text · Book |
| REF‑MKT‑07 | Salon Marketing | — | Reference text · Book |
| REF‑CX‑01 | Customer Service in Health Care | Kristin Baird | Reference text · Book |
| REF‑CX‑02 | Can Your Customer Service Do This? | — | Reference text · Book |
| REF‑CX‑03 | Crushing the Competition with Service | — | Reference text · Book |
| REF‑CX‑04 | Customer Service Is Just Foreplay | Jason D. Cass | Supplementary text · Book |
| REF‑FIN‑01 | J.K. Lasser's Small Business Taxes 2025 | — | Reference text · Book |
| REF‑FIN‑02 | Tax Accounting: A Guide for Small Business Owners | — | Reference text · Book |
| REF‑FIN‑03 | Small Time Operator | — | Reference text · Book |
| REF‑FIN‑04 | 475 Tax Deductions for All Small Businesses | — | Reference text · Book |
| REF‑LEG‑01 | Cybersecurity: Ethics, Legal, Risks | Ishaani Priyadarshini | Reference text · Book |
| REF‑LEG‑02 | The Tax and Legal Playbook | Mark J. Kohler | Reference text · Book |
| REF‑LEG‑03 | Reimagining Fairness: Equity, Cultural DiverPPSy, and Inclusion Competency Approach | — | Reference text · Book |
| REF‑LEG‑04 | PCI Compliance | Dr. Branden R. Williams | Reference text · Book |
| REF‑LEG‑05 | The Guide to OSHA Compliance | Robert D. Peterson | Reference text · Book |
| REF‑LEG‑06 | Security-First Compliance for Small Businesses | — | Reference text · Book |
| REF‑LEG‑07 | Transfer Pricing: Rules, Compliance and Controversy | — | Supplementary text · Book |
| REF‑LEG‑08 | Stop Harming Customers: A Compliance Manifesto | David Silverman | Reference text · Book |
| REF‑LEG‑09 | Tools of Effective Compliance | Thomas Schneider | Reference text · Book |
| REF‑LSH‑01 | Teaching life skills in intermediate phase | — | Reference text · Book |
| REF‑LSH‑02 | Stuff Students Should Know: Learn Essential Life Skills | — | Reference text · Book |
| REF‑LSH‑03 | 10 Proven Ways to Relieve Stress Now | — | Supplementary text · Book |
| REF‑LSH‑04 | Personal Finance | — | Reference text · Book |
| REF‑PER‑01 | The Personal MBA | Josh Kaufman | Reference text · Book |
| REF‑PER‑02 | Self-Talk Your Way to Success | Kam Knight | Reference text · Book |
| REF‑PER‑03 | Are You Ready to Succeed? | — | Reference text · Book |
| REF‑PER‑04 | Trigger High Performance | — | Reference text · Book |
| REF‑PER‑05 | Rebuilding Relationships in Recovery | — | Reference text · Book |
| REF‑PER‑06 | Trust Yourself: Stop Overthinking and Channel Your Emotions for Success at Work | — | Reference text · Book |
| REF‑AI‑02 | LinkedIn Personal Branding and Marketing | — | Reference text · Book |
| REF‑AI‑03 | The Marketing Mindset: 100 ChatGPT Prompts | — | Reference text · Book |
| REF‑AI‑04 | Enterprise AI | Shazia Sadiq | Reference text · Book |
| REF‑AI‑05 | AI In Finance | Krishan Arora | Reference text · Book |
| REF‑AI‑06 | AI Timekeeper | Robert Breeser | Reference text · Book |
| REF‑AI‑07 | AI Profit Hacks | — | Reference text · Book |
| REF‑AI‑08 | AI Startup Strategy | Adhiguna Mahendra | Reference text · Book |
| REF‑AI‑09 | AI and the Boardroom | Rohan Sharma | Reference text · Book |
| REF‑AI‑10 | Foundations of Agentic AI for Retail | — | Reference text · Book |
| REF‑AI‑11 | Retail 4.0: How AI is Shaping the Future of Shopping | — | Supplementary text · Book |
| REF‑AI‑12 | AI-Powered Accounting with Excel and Power BI | — | Reference text · Book |
| REF‑AI‑13 | The AI Revolution in Customer Service | — | Reference text · Book |
| REF‑AI‑14 | Natural Language Processing with Python: Building your Own Customer Service ChatBot | — | Reference text · Book |
| REF‑AI‑15 | Teaching and Learning in the Age of Generative AI | — | Reference text · Book |

# B3. Syllabus —  Animal Care Assistant ACA

## Course Information

| Program / code | Animal Care Assistant ACA |
| --- | --- |
| Credential | Dog Bather–Animal Care Assistant Diploma (Diploma) |
| Clock hours | 988 total — technical 112 · business & personal 864 · applied capstone 12 |
| Scheduled length | 35 weeks full-time (30 hr/wk, Mon–Fri 08:00–15:30) · ≈ 66 weeks part-time (15 hr/wk, evenings/Saturday) |
| Program objective | Identify a puppy and understand puppy life · Recognize breeds · Recognize grooming tools · Identify workplace safety · Provide basic handling and basic dog care · Understand sanitation process · Enter the workforce with personal readiness and customer-service skills · Understand the bather-to-owner career ladder. |
| Admission | Age 18+ (17 with guardian consent); high-school diploma, GED or ability-to-benefit assessment; physical ability to lift 40 lb and stand for lab blocks; signed animal-handling risk acknowledgement |
| Instructional team | Animal care instructor (technical, ACA-BIZ panel) · Business instructor · Personal readiness coach · Technology & AI lead |
| Required materials | Professional Dog Groomer Tools kit (catalog Section 9) · Owner-Operator Toolkit sanACAox accounts · laptop or tablet |
| Required texts | 8 core manuals; 68 reference and supplementary texts (Required & Reference Texts below) |
| Attendance policy | Clock hours are earned only for attended blocks. Minimum 95% attendance per term; missed lab hours are made up in Friday open lab within the same term. Below 90% at any checkpoint triggers a coach meeting and written plan. |
| Grading | Module: 10 activities + 10 micro-checks , 2 checkpoints and final quiz at ≥ 80%, capstone artifact accepted. Program: Competency Rubric at Competent on every row (catalog Section 9); safety-critical rows are pass/fail. |
| Safety gates | ACA-201 signed off before live-animal work; CPR/First Aid before practicum |
| Completion requirements | All 150 modules · 988 clock hours recorded · rubric Competent · ACA-BIZ capstone passed by panel · practicum log signed |
| Stacks into | IPDG (ACA-101/102/103/201/301 credited toward IPDG-101–204); all business & personal modules credited |

## Term Outline

| Term | Technical modules | Business & personal modules | Applied | Hrs: tech / biz / applied | Term hours |
| --- | --- | --- | --- | --- | --- |
| Term 1 — Foundation | ACA-101, ACA-102, ACA-103 | 36 modules: LSH 101–105, PER 101–105, BUS 101–106, MKT 101–105, TEC 101–105, FIN 101–105, LEG 101–105 | — | 32 / 216 / 0 | 248 (≈9 wk) |
| Term 2 — Core Skill | ACA-201 | 36 modules: LSH 201–205, PER 201–205, BUS 201–206, MKT 201–205, TEC 201–205, FIN 201–205, LEG 201–205 | — | 30 / 216 / 0 | 246 (≈9 wk) |
| Term 3 — Advanced Skill | ACA-301 | 36 modules: LSH 301–305, PER 301–305, BUS 301–306, MKT 301–305, TEC 301–305, FIN 301–305, LEG 301–305 | — | 50 / 216 / 0 | 266 (≈9 wk) |
| Term 4 — Capstone | — | 36 modules: LSH 401–405, PER 401–405, BUS 401–406, MKT 401–405, TEC 401–405, FIN 401–405, LEG 401–405 | ACA-BIZ | 0 / 216 / 12 | 228 (≈8 wk) |
| Program total |  |  |  | 112 / 864 / 12 | 988 (≈33 wk) |

## Week-by-Week Schedule

Hours column = technical / business & personal clock hours per week. "(cont.)" = module continues into the next week. Quizzes are taken in the week a module closes; level checkpoints and rubric reviews close each term.

| Week | Term | Technical modules | Business & personal modules | Hrs | Assessments this week |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | T1 Foundation | ACA‑101 (cont.) | LSH‑101, LSH‑102, LSH‑103, LSH‑104 | 4 / 24 | Quizzes: LSH‑101, LSH‑102, LSH‑103, LSH‑104 |
| Wk 2 | T1 Foundation | ACA‑101, ACA‑102 (cont.) | LSH‑105, PER‑101, PER‑102, PER‑103 | 4 / 24 | Quizzes: ACA‑101, LSH‑105, PER‑101, PER‑102, PER‑103 |
| Wk 3 | T1 Foundation | ACA‑102 (cont.) | PER‑104, PER‑105, BUS‑101, BUS‑102 | 4 / 24 | Quizzes: PER‑104, PER‑105, BUS‑101, BUS‑102 |
| Wk 4 | T1 Foundation | ACA‑102 (cont.) | BUS‑103, BUS‑104, BUS‑105, BUS‑106 | 4 / 24 | Quizzes: BUS‑103, BUS‑104, BUS‑105, BUS‑106 |
| Wk 5 | T1 Foundation | ACA‑102 (cont.) | MKT‑101, MKT‑102, MKT‑103, MKT‑104 | 4 / 24 | Quizzes: MKT‑101, MKT‑102, MKT‑103, MKT‑104 |
| Wk 6 | T1 Foundation | ACA‑102 (cont.) | MKT‑105, TEC‑101, TEC‑102, TEC‑103 | 4 / 24 | Quizzes: MKT‑105, TEC‑101, TEC‑102, TEC‑103 |
| Wk 7 | T1 Foundation | ACA‑102 (cont.) | TEC‑104, TEC‑105, FIN‑101, FIN‑102 | 4 / 24 | Quizzes: TEC‑104, TEC‑105, FIN‑101, FIN‑102 |
| Wk 8 | T1 Foundation | ACA‑102, ACA‑103 (cont.) | FIN‑103, FIN‑104, FIN‑105, LEG‑101 | 4 / 24 | Quizzes: ACA‑102, FIN‑103, FIN‑104, FIN‑105, LEG‑101 |
| Wk 9 | T1 Foundation | ACA‑103 | LEG‑102, LEG‑103, LEG‑104, LEG‑105 | 4 / 24 | Quizzes: ACA‑103, LEG‑102, LEG‑103, LEG‑104, LEG‑105 · Level checkpoint · rubric review |
| Wk 10 | T2 Core Skill | ACA‑201 (cont.) | LSH‑201, LSH‑202, LSH‑203, LSH‑204 | 3 / 24 | Quizzes: LSH‑201, LSH‑202, LSH‑203, LSH‑204 |
| Wk 11 | T2 Core Skill | ACA‑201 (cont.) | LSH‑205, PER‑201, PER‑202, PER‑203 | 3 / 24 | Quizzes: LSH‑205, PER‑201, PER‑202, PER‑203 |
| Wk 12 | T2 Core Skill | ACA‑201 (cont.) | PER‑204, PER‑205, BUS‑201, BUS‑202 | 3 / 24 | Quizzes: PER‑204, PER‑205, BUS‑201, BUS‑202 |
| Wk 13 | T2 Core Skill | ACA‑201 (cont.) | BUS‑203, BUS‑204, BUS‑205, BUS‑206 | 3 / 24 | Quizzes: BUS‑203, BUS‑204, BUS‑205, BUS‑206 |
| Wk 14 | T2 Core Skill | ACA‑201 (cont.) | MKT‑201, MKT‑202, MKT‑203, MKT‑204 | 3 / 24 | Quizzes: MKT‑201, MKT‑202, MKT‑203, MKT‑204 |
| Wk 15 | T2 Core Skill | ACA‑201 (cont.) | MKT‑205, TEC‑201, TEC‑202, TEC‑203 | 3 / 24 | Quizzes: MKT‑205, TEC‑201, TEC‑202, TEC‑203 |
| Wk 16 | T2 Core Skill | ACA‑201 (cont.) | TEC‑204, TEC‑205, FIN‑201, FIN‑202 | 3 / 24 | Quizzes: TEC‑204, TEC‑205, FIN‑201, FIN‑202 |
| Wk 17 | T2 Core Skill | ACA‑201 (cont.) | FIN‑203, FIN‑204, FIN‑205, LEG‑201 | 3 / 24 | Quizzes: FIN‑203, FIN‑204, FIN‑205, LEG‑201 |
| Wk 18 | T2 Core Skill | ACA‑201 | LEG‑202, LEG‑203, LEG‑204, LEG‑205 | 3 / 24 | Quizzes: ACA‑201, LEG‑202, LEG‑203, LEG‑204, LEG‑205 · Level checkpoint · rubric review |
| Wk 19 | T3 Advanced Skill | ACA‑301 (cont.) | LSH‑301, LSH‑302, LSH‑303, LSH‑304 | 6 / 24 | Quizzes: LSH‑301, LSH‑302, LSH‑303, LSH‑304 |
| Wk 20 | T3 Advanced Skill | ACA‑301 (cont.) | LSH‑305, PER‑301, PER‑302, PER‑303 | 6 / 24 | Quizzes: LSH‑305, PER‑301, PER‑302, PER‑303 |
| Wk 21 | T3 Advanced Skill | ACA‑301 (cont.) | PER‑304, PER‑305, BUS‑301, BUS‑302 | 6 / 24 | Quizzes: PER‑304, PER‑305, BUS‑301, BUS‑302 |
| Wk 22 | T3 Advanced Skill | ACA‑301 (cont.) | BUS‑303, BUS‑304, BUS‑305, BUS‑306 | 6 / 24 | Quizzes: BUS‑303, BUS‑304, BUS‑305, BUS‑306 |
| Wk 23 | T3 Advanced Skill | ACA‑301 (cont.) | MKT‑301, MKT‑302, MKT‑303, MKT‑304 | 6 / 24 | Quizzes: MKT‑301, MKT‑302, MKT‑303, MKT‑304 |
| Wk 24 | T3 Advanced Skill | ACA‑301 (cont.) | MKT‑305, TEC‑301, TEC‑302, TEC‑303 | 6 / 24 | Quizzes: MKT‑305, TEC‑301, TEC‑302, TEC‑303 |
| Wk 25 | T3 Advanced Skill | ACA‑301 (cont.) | TEC‑304, TEC‑305, FIN‑301, FIN‑302 | 6 / 24 | Quizzes: TEC‑304, TEC‑305, FIN‑301, FIN‑302 |
| Wk 26 | T3 Advanced Skill | ACA‑301 (cont.) | FIN‑303, FIN‑304, FIN‑305, LEG‑301 | 6 / 24 | Quizzes: FIN‑303, FIN‑304, FIN‑305, LEG‑301 |
| Wk 27 | T3 Advanced Skill | ACA‑301 | LEG‑302, LEG‑303, LEG‑304, LEG‑305 | 6 / 24 | Quizzes: ACA‑301, LEG‑302, LEG‑303, LEG‑304, LEG‑305 · Level checkpoint · rubric review |
| Wk 28 | T4 Capstone | — | LSH‑401, LSH‑402, LSH‑403, LSH‑404, LSH‑405 (cont.) | 0 / 29 | Quizzes: LSH‑401, LSH‑402, LSH‑403, LSH‑404 |
| Wk 29 | T4 Capstone | — | LSH‑405, PER‑401, PER‑402, PER‑403, PER‑404, PER‑405 (cont.) | 0 / 29 | Quizzes: LSH‑405, PER‑401, PER‑402, PER‑403, PER‑404 |
| Wk 30 | T4 Capstone | — | PER‑405, BUS‑401, BUS‑402, BUS‑403, BUS‑404, BUS‑405 (cont.) | 0 / 29 | Quizzes: PER‑405, BUS‑401, BUS‑402, BUS‑403, BUS‑404 |
| Wk 31 | T4 Capstone | — | BUS‑405, BUS‑406, MKT‑401, MKT‑402, MKT‑403 | 0 / 29 | Quizzes: BUS‑405, BUS‑406, MKT‑401, MKT‑402, MKT‑403 |
| Wk 32 | T4 Capstone | — | MKT‑404, MKT‑405, TEC‑401, TEC‑402, TEC‑403 (cont.) | 0 / 29 | Quizzes: MKT‑404, MKT‑405, TEC‑401, TEC‑402 |
| Wk 33 | T4 Capstone | — | TEC‑403, TEC‑404, TEC‑405, FIN‑401, FIN‑402, FIN‑403 (cont.) | 0 / 29 | Quizzes: TEC‑403, TEC‑404, TEC‑405, FIN‑401, FIN‑402 |
| Wk 34 | T4 Capstone | — | FIN‑403, FIN‑404, FIN‑405, LEG‑401, LEG‑402, LEG‑403 (cont.) | 0 / 29 | Quizzes: FIN‑403, FIN‑404, FIN‑405, LEG‑401, LEG‑402 |
| Wk 35 | T4 Capstone | — | LEG‑403, LEG‑404, LEG‑405, ACA‑BIZ | 0 / 29 | Quizzes: LEG‑403, LEG‑404, LEG‑405, ACA‑BIZ · Level checkpoint · rubric review · Capstone panel · practicum sign-off |

## Assessment Calendar

| Point | When | Instrument | Pass standard |
| --- | --- | --- | --- |
| Module quizzes and checkpoints | Week each module closes (see schedule) | Final quiz + 2 checkpoints + capstone artifact | ≥ 80%; artifact accepted |
| Level checkpoint 1 | Last week of Term 1 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 2 | Last week of Term 2 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 3 | Last week of Term 3 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 4 | Last week of Term 4 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Safety-critical sign-off | Before first live-animal service | Instructor checklist (handling, sanitation, CPR/First Aid) | Pass/fail |
| Practicum | Final term | Supervised practicum log | Minimums met and supervisor signature |
| Applied business capstone | Final week — ACA-BIZ | Instructor + owner panel | Launch plan, price menu, licensing/insurance worksheet, 90-day calendar accepted |

## Required & Reference Texts

| ID | Title | Author / publisher | Type |
| --- | --- | --- | --- |
| MAN‑ACA | Bather–Animal Care Assistant | Leashed program manual | Core manual |
| MAN‑LSH | Life Skills & Personal Readiness | Leashed program manual | Core manual |
| MAN‑BUS | Business & Leadership: Ownership, Operations & Expansion (merged BUS + LDR) | Leashed program manual | Core manual |
| MAN‑PER | Personal MaSittery & Lifelong Growth | Leashed program manual | Core manual |
| MAN‑MKT | Marketing, Branding & SEO MaSittery | Leashed program manual | Core manual |
| MAN‑TEC | AI & Technology Systems | Leashed program manual | Core manual |
| MAN‑FIN | Financial MaSittery, Bookkeeping & Tax Strategy | Leashed program manual | Core manual |
| MAN‑LEG | Legal, Risk, Compliance & Ethical Governance | Leashed program manual | Core manual |
| REF‑GRM‑01 | Dog Grooming for Beginners | Jorge Bendersky | Reference text · Book |
| REF‑GRM‑02 | Grooming Manual for Dog and Cat | — | Reference text · DOCX manuscript |
| REF‑GRM‑03 | The Everything Dog Grooming Book | — | Reference text · DOCX manuscript |
| REF‑BEH‑01 | HanACAook of Applied Dog Behavior and Training, Vol. 3 | Steven R. Lindsay | Reference text · Book |
| REF‑GRM‑04 | The Stone Guide to Dog Grooming for All Breeds | Ben Stone | Reference text · Book |
| REF‑PPS‑01 | Pet Care Givers and Families | — | Reference text · Book |
| REF‑HLTH‑01 | National Geographic Guide to Pet Health, Behavior, and Happiness | — | Reference text · Book |
| REF‑AI‑01 | AI for Animals: Revolutionizing Veterinary Care | Amelia Hawkins | Supplementary text · Book |
| REF‑ANI‑01 | Beastly: The 40,000-Year Story of Animals and Us | — | Supplementary text · Book |
| REF‑CARE‑01 | Knack Dog Care and Training | — | Reference text · Book |
| REF‑BIZ‑01 | Business Cycles | Francis X. Diebold | Supplementary text · Book |
| REF‑BIZ‑02 | Building a Successful Business | Dominik Mikulaschek | Reference text · Book |
| REF‑BIZ‑03 | The Disruptors | Sally Percy | Supplementary text · Book |
| REF‑BIZ‑04 | Go It Alone! | Bruce Judson | Reference text · Book |
| REF‑BIZ‑05 | The Successful Entrepreneur Playbook | Paul H. Woodruff | Reference text · Book |
| REF‑BIZ‑06 | 4-Hour Work Day | — | Supplementary text · Book |
| REF‑BIZ‑07 | The Business Bible | — | Reference text · Book |
| REF‑BIZ‑08 | Poverty Traps | Samuel Bowles | Supplementary text · Book |
| REF‑LDR‑01 | Leadership Presence | Belle Linda Halpern | Reference text · Book |
| REF‑LDR‑02 | Leadership and Ethics | Jacqueline Boaks | Reference text · Book |
| REF‑MKT‑01 | Multi-Channel Marketing, Branding and Retail Design | — | Reference text · Book |
| REF‑MKT‑02 | Marketing is not Rocket Science | — | Reference text · Book |
| REF‑MKT‑03 | Unconscious Branding | Douglas Van Praet | Supplementary text · Book |
| REF‑MKT‑04 | Content Branding Solutions for Entrepreneur Strategic Content Marketing | Peter Lucking | Reference text · Book |
| REF‑MKT‑05 | Branding: What You Need to Know About Building a Personal Brand… | — | Reference text · Book |
| REF‑MKT‑06 | Business Branding Guide | — | Reference text · Book |
| REF‑MKT‑07 | Salon Marketing | — | Reference text · Book |
| REF‑CX‑01 | Customer Service in Health Care | Kristin Baird | Reference text · Book |
| REF‑CX‑02 | Can Your Customer Service Do This? | — | Reference text · Book |
| REF‑CX‑03 | Crushing the Competition with Service | — | Reference text · Book |
| REF‑CX‑04 | Customer Service Is Just Foreplay | Jason D. Cass | Supplementary text · Book |
| REF‑FIN‑01 | J.K. Lasser's Small Business Taxes 2025 | — | Reference text · Book |
| REF‑FIN‑02 | Tax Accounting: A Guide for Small Business Owners | — | Reference text · Book |
| REF‑FIN‑03 | Small Time Operator | — | Reference text · Book |
| REF‑FIN‑04 | 475 Tax Deductions for All Small Businesses | — | Reference text · Book |
| REF‑LEG‑01 | Cybersecurity: Ethics, Legal, Risks | Ishaani Priyadarshini | Reference text · Book |
| REF‑LEG‑02 | The Tax and Legal Playbook | Mark J. Kohler | Reference text · Book |
| REF‑LEG‑03 | Reimagining Fairness: Equity, Cultural DiverPPSy, and Inclusion Competency Approach | — | Reference text · Book |
| REF‑LEG‑04 | PCI Compliance | Dr. Branden R. Williams | Reference text · Book |
| REF‑LEG‑05 | The Guide to OSHA Compliance | Robert D. Peterson | Reference text · Book |
| REF‑LEG‑06 | Security-First Compliance for Small Businesses | — | Reference text · Book |
| REF‑LEG‑07 | Transfer Pricing: Rules, Compliance and Controversy | — | Supplementary text · Book |
| REF‑LEG‑08 | Stop Harming Customers: A Compliance Manifesto | David Silverman | Reference text · Book |
| REF‑LEG‑09 | Tools of Effective Compliance | Thomas Schneider | Reference text · Book |
| REF‑LSH‑01 | Teaching life skills in intermediate phase | — | Reference text · Book |
| REF‑LSH‑02 | Stuff Students Should Know: Learn Essential Life Skills | — | Reference text · Book |
| REF‑LSH‑03 | 10 Proven Ways to Relieve Stress Now | — | Supplementary text · Book |
| REF‑LSH‑04 | Personal Finance | — | Reference text · Book |
| REF‑PER‑01 | The Personal MBA | Josh Kaufman | Reference text · Book |
| REF‑PER‑02 | Self-Talk Your Way to Success | Kam Knight | Reference text · Book |
| REF‑PER‑03 | Are You Ready to Succeed? | — | Reference text · Book |
| REF‑PER‑04 | Trigger High Performance | — | Reference text · Book |
| REF‑PER‑05 | Rebuilding Relationships in Recovery | — | Reference text · Book |
| REF‑PER‑06 | Trust Yourself: Stop Overthinking and Channel Your Emotions for Success at Work | — | Reference text · Book |
| REF‑AI‑02 | LinkedIn Personal Branding and Marketing | — | Reference text · Book |
| REF‑AI‑03 | The Marketing Mindset: 100 ChatGPT Prompts | — | Reference text · Book |
| REF‑AI‑04 | Enterprise AI | Shazia Sadiq | Reference text · Book |
| REF‑AI‑05 | AI In Finance | Krishan Arora | Reference text · Book |
| REF‑AI‑06 | AI Timekeeper | Robert Breeser | Reference text · Book |
| REF‑AI‑07 | AI Profit Hacks | — | Reference text · Book |
| REF‑AI‑08 | AI Startup Strategy | Adhiguna Mahendra | Reference text · Book |
| REF‑AI‑09 | AI and the Boardroom | Rohan Sharma | Reference text · Book |
| REF‑AI‑10 | Foundations of Agentic AI for Retail | — | Reference text · Book |
| REF‑AI‑11 | Retail 4.0: How AI is Shaping the Future of Shopping | — | Supplementary text · Book |
| REF‑AI‑12 | AI-Powered Accounting with Excel and Power BI | — | Reference text · Book |
| REF‑AI‑13 | The AI Revolution in Customer Service | — | Reference text · Book |
| REF‑AI‑14 | Natural Language Processing with Python: Building your Own Customer Service ChatBot | — | Reference text · Book |
| REF‑AI‑15 | Teaching and Learning in the Age of Generative AI | — | Reference text · Book |

# B4. Syllabus — Professional Pet PPSitter PPS

## Course Information

| Program / code | Professional Pet PPSitter PPS |
| --- | --- |
| Credential | Pet PPSitter Certificate (Certificate) |
| Clock hours | 56 total — technical 14 · business & personal 36 · applied capstone 6 |
| Scheduled length | 2 weeks full-time (30 hr/wk, Mon–Fri 08:00–15:30) · ≈ 4 weeks part-time (15 hr/wk, evenings/Saturday) |
| Program objective | Introduce and choose appropriate clients · Provide multi-species pet care · Handle pets and sanitation safely · Provide CPR and first aid · Launch and run a compliant, insured pet-PPSting business. |
| Admission | Age 18+; background check (in-home client access); reliable transportation; signed animal-handling risk acknowledgement |
| Instructional team | Animal care instructor (technical, PPS-BIZ panel) · Business instructor |
| Required materials | Pet-PPSting field kit: leash, slip lead, first-aid kit, waste bags, client key log · Owner-Operator Toolkit sanACAox accounts · laptop or tablet |
| Required texts | 5 core manuals; 15 reference and supplementary texts (Required & Reference Texts below) |
| Attendance policy | Clock hours are earned only for attended blocks. Minimum 95% attendance per term; missed lab hours are made up in Friday open lab within the same term. Below 90% at any checkpoint triggers a coach meeting and written plan. |
| Grading | Module: 10 activities + 10 micro-checks , 2 checkpoints and final quiz at ≥ 80%, capstone artifact accepted. Program: Competency Rubric at Competent on every row (catalog Section 9); safety-critical rows are pass/fail. |
| Safety gates | PPS-104, PPS-105 signed off before live-animal work |
| Completion requirements | All 11 modules · 56 clock hours recorded · rubric Competent · PPS-BIZ capstone passed by panel |
| Stacks into | ACA, IPDG, PDT or PPC (PPS-101–105 and the 6 micro-owner modules credited) |

## Term Outline

| Term | Technical modules | Business & personal modules | Applied | Hrs: tech / biz / applied | Term hours |
| --- | --- | --- | --- | --- | --- |
| Term 1 — Foundation | PPS-101, PPS-102, PPS-104, PPS-105 | BUS-101, FIN-101, LEG-101, LEG-103 | — | 14 / 24 / 0 | 38 (≈2 wk) |
| Term 2 — Core Skill | — | BUS-203 | — | 0 / 6 / 0 | 6 (≈1 day) |
| Term 3 — Advanced Skill | — | MKT-304 | — | 0 / 6 / 0 | 6 (≈1 day) |
| Term 4 — Capstone | — | — | PPS-BIZ | 0 / 0 / 6 | 6 (≈1 day) |
| Program total |  |  |  | 14 / 36 / 6 | 56 (≈2 wk) |

## Week-by-Week Schedule

Hours column = technical / business & personal clock hours per week. "(cont.)" = module continues into the next week. Quizzes are taken in the week a module closes; level checkpoints and rubric reviews close each term.

| Week | Term | Technical modules | Business & personal modules | Hrs | Assessments this week |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | T1 All levels | PPS‑101, PPS‑102, PPS‑104, PPS‑105 (cont.) | BUS‑101, FIN‑101, LEG‑101, LEG‑103 (cont.) | 7 / 21 | Quizzes: PPS‑101, PPS‑102, PPS‑104, BUS‑101, FIN‑101, LEG‑101 |
| Wk 2 | T1 All levels | PPS‑105 | LEG‑103, BUS‑203, MKT‑304, PPS‑BIZ | 7 / 21 | Quizzes: PPS‑105, LEG‑103, BUS‑203, MKT‑304, PPS‑BIZ · Level checkpoint · rubric review · Capstone panel · practicum sign-off |

## Assessment Calendar

| Point | When | Instrument | Pass standard |
| --- | --- | --- | --- |
| Module quizzes and checkpoints | Week each module closes (see schedule) | Final quiz + 2 checkpoints + capstone artifact | ≥ 80%; artifact accepted |
| Level checkpoint 1 | Last week of Term 1 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 2 | Last week of Term 2 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 3 | Last week of Term 3 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 4 | Last week of Term 4 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Safety-critical sign-off | Before first live-animal service | Instructor checklist (handling, sanitation, CPR/First Aid) | Pass/fail |
| Applied business capstone | Final week — PPS-BIZ | Instructor + owner panel | Launch plan, price menu, licensing/insurance worksheet, 90-day calendar accepted |

## Required & Reference Texts

| ID | Title | Author / publisher | Type |
| --- | --- | --- | --- |
| MAN‑PPS | Professional Pet PPSitter | Leashed program manual | Core manual |
| MAN‑BUS | Business & Leadership: Ownership, Operations & Expansion (merged BUS + LDR) | Leashed program manual | Core manual |
| MAN‑MKT | Marketing, Branding & SEO MaSittery | Leashed program manual | Core manual |
| MAN‑FIN | Financial MaSittery, Bookkeeping & Tax Strategy | Leashed program manual | Core manual |
| MAN‑LEG | Legal, Risk, Compliance & Ethical Governance | Leashed program manual | Core manual |
| REF‑PPS‑01 | Pet Care Givers and Families | — | Reference text · Book |
| REF‑HLTH‑01 | National Geographic Guide to Pet Health, Behavior, and Happiness | — | Reference text · Book |
| REF‑MED‑01 | Small Animal Critical Care Medicine | — | Reference text · Book |
| REF‑CARE‑01 | Knack Dog Care and Training | — | Reference text · Book |
| REF‑BIZ‑02 | Building a Successful Business | Dominik Mikulaschek | Reference text · Book |
| REF‑BIZ‑04 | Go It Alone! | Bruce Judson | Reference text · Book |
| REF‑BIZ‑07 | The Business Bible | — | Reference text · Book |
| REF‑LDR‑02 | Leadership and Ethics | Jacqueline Boaks | Reference text · Book |
| REF‑MKT‑07 | Salon Marketing | — | Reference text · Book |
| REF‑FIN‑03 | Small Time Operator | — | Reference text · Book |
| REF‑LEG‑02 | The Tax and Legal Playbook | Mark J. Kohler | Reference text · Book |
| REF‑LEG‑05 | The Guide to OSHA Compliance | Robert D. Peterson | Reference text · Book |
| REF‑LEG‑08 | Stop Harming Customers: A Compliance Manifesto | David Silverman | Reference text · Book |
| REF‑LSH‑04 | Personal Finance | — | Reference text · Book |
| REF‑PER‑01 | The Personal MBA | Josh Kaufman | Reference text · Book |

# B5. Syllabus — Professional Cat Groomer (CAT)

## Course Information

| Program / code | Professional Cat Groomer (CAT) |
| --- | --- |
| Credential | Professional Cat Groomer Certificate (Certificate) |
| Clock hours | 58 total — technical 16 · business & personal 36 · applied capstone 6 |
| Scheduled length | 2 weeks full-time (30 hr/wk, Mon–Fri 08:00–15:30) · ≈ 4 weeks part-time (15 hr/wk, evenings/Saturday) |
| Program objective | Recognize cat breeds · Read cat temperament and handle safely · Bathe and dry cats safely · Perform short, long and shave-down cat grooms · Add a profitable, safe cat-grooming service line to a business. |
| Admission | Age 18+; prior grooming experience or ACA/IPDG enrollment recommended; signed animal-handling risk acknowledgement |
| Instructional team | Grooming instructor (technical, CAT-BIZ panel) · Business instructor |
| Required materials | Professional Dog Groomer Tools kit (catalog Section 9) · Owner-Operator Toolkit sanACAox accounts · laptop or tablet |
| Required texts | 5 core manuals; 13 reference and supplementary texts (Required & Reference Texts below) |
| Attendance policy | Clock hours are earned only for attended blocks. Minimum 95% attendance per term; missed lab hours are made up in Friday open lab within the same term. Below 90% at any checkpoint triggers a coach meeting and written plan. |
| Grading | Module: 10 activities + 10 micro-checks , 2 checkpoints and final quiz at ≥ 80%, capstone artifact accepted. Program: Competency Rubric at Competent on every row (catalog Section 9); safety-critical rows are pass/fail. |
| Safety gates | CAT-102 signed off before live-animal work |
| Completion requirements | All 11 modules · 58 clock hours recorded · rubric Competent · CAT-BIZ capstone passed by panel |
| Stacks into | IPDG or PPC (CAT-101–104 and the 6 micro-owner modules credited) |

## Term Outline

| Term | Technical modules | Business & personal modules | Applied | Hrs: tech / biz / applied | Term hours |
| --- | --- | --- | --- | --- | --- |
| Term 1 — Foundation | CAT-101, CAT-102, CAT-103, CAT-104 | BUS-101, FIN-101, LEG-101, LEG-103 | — | 16 / 24 / 0 | 40 (≈2 wk) |
| Term 2 — Core Skill | — | BUS-203 | — | 0 / 6 / 0 | 6 (≈1 day) |
| Term 3 — Advanced Skill | — | MKT-304 | — | 0 / 6 / 0 | 6 (≈1 day) |
| Term 4 — Capstone | — | — | CAT-BIZ | 0 / 0 / 6 | 6 (≈1 day) |
| Program total |  |  |  | 16 / 36 / 6 | 58 (≈2 wk) |

## Week-by-Week Schedule

Hours column = technical / business & personal clock hours per week. "(cont.)" = module continues into the next week. Quizzes are taken in the week a module closes; level checkpoints and rubric reviews close each term.

| Week | Term | Technical modules | Business & personal modules | Hrs | Assessments this week |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | T1 All levels | CAT‑101, CAT‑102 | BUS‑101, FIN‑101, LEG‑101, LEG‑103 (cont.) | 8 / 21 | Quizzes: CAT‑101, CAT‑102, BUS‑101, FIN‑101, LEG‑101 |
| Wk 2 | T1 All levels | CAT‑103, CAT‑104 | LEG‑103, BUS‑203, MKT‑304, CAT‑BIZ | 8 / 21 | Quizzes: CAT‑103, CAT‑104, LEG‑103, BUS‑203, MKT‑304, CAT‑BIZ · Level checkpoint · rubric review · Capstone panel · practicum sign-off |

## Assessment Calendar

| Point | When | Instrument | Pass standard |
| --- | --- | --- | --- |
| Module quizzes and checkpoints | Week each module closes (see schedule) | Final quiz + 2 checkpoints + capstone artifact | ≥ 80%; artifact accepted |
| Level checkpoint 1 | Last week of Term 1 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 2 | Last week of Term 2 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 3 | Last week of Term 3 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 4 | Last week of Term 4 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Safety-critical sign-off | Before first live-animal service | Instructor checklist (handling, sanitation, CPR/First Aid) | Pass/fail |
| Applied business capstone | Final week — CAT-BIZ | Instructor + owner panel | Launch plan, price menu, licensing/insurance worksheet, 90-day calendar accepted |

## Required & Reference Texts

| ID | Title | Author / publisher | Type |
| --- | --- | --- | --- |
| MAN‑CAT | Professional Cat Groomer | Leashed program manual | Core manual |
| MAN‑BUS | Business & Leadership: Ownership, Operations & Expansion (merged BUS + LDR) | Leashed program manual | Core manual |
| MAN‑MKT | Marketing, Branding & SEO MaSittery | Leashed program manual | Core manual |
| MAN‑FIN | Financial MaSittery, Bookkeeping & Tax Strategy | Leashed program manual | Core manual |
| MAN‑LEG | Legal, Risk, Compliance & Ethical Governance | Leashed program manual | Core manual |
| REF‑GRM‑02 | Grooming Manual for Dog and Cat | — | Reference text · DOCX manuscript |
| REF‑GRM‑04 | The Stone Guide to Dog Grooming for All Breeds | Ben Stone | Reference text · Book |
| REF‑HLTH‑01 | National Geographic Guide to Pet Health, Behavior, and Happiness | — | Reference text · Book |
| REF‑BIZ‑02 | Building a Successful Business | Dominik Mikulaschek | Reference text · Book |
| REF‑BIZ‑04 | Go It Alone! | Bruce Judson | Reference text · Book |
| REF‑BIZ‑07 | The Business Bible | — | Reference text · Book |
| REF‑LDR‑02 | Leadership and Ethics | Jacqueline Boaks | Reference text · Book |
| REF‑MKT‑07 | Salon Marketing | — | Reference text · Book |
| REF‑FIN‑03 | Small Time Operator | — | Reference text · Book |
| REF‑LEG‑02 | The Tax and Legal Playbook | Mark J. Kohler | Reference text · Book |
| REF‑LEG‑08 | Stop Harming Customers: A Compliance Manifesto | David Silverman | Reference text · Book |
| REF‑LSH‑04 | Personal Finance | — | Reference text · Book |
| REF‑PER‑01 | The Personal MBA | Josh Kaufman | Reference text · Book |

# B6. Syllabus —  Professional Pet Care & Business Ownership PPC

## Course Information

| Program / code | Professional Pet Care & Business Ownership PPC |
| --- | --- |
| Credential | Professional Pet Care & Business Ownership — Advanced Diploma (Advanced Diploma) |
| Clock hours | 1,500 total — technical 600 · business & personal 864 · applied capstone 36 |
| Scheduled length | 52 weeks full-time (30 hr/wk, Mon–Fri 08:00–15:30) · ≈ 100 weeks part-time (15 hr/wk, evenings/Saturday) |
| Program objective | All IPDG, PDT, PPS and CAT technical objectives · a multi-service practicum across salon floor, training floor and PPSitter viPPSs · MaSitter the full Business & Personal MaSittery spine (LSH, PER, BUS, MKT, TEC, FIN, LEG) · Launch, fund, staff, market, protect and scale a multi-service pet-care enterprise · MaSitter personal life systems, finances and well-being as a whole-person owner · Provide CPR and first aid. |
| Admission | Age 18+ (17 with guardian consent); high-school diploma, GED or ability-to-benefit assessment; physical ability to lift 40 lb and stand for lab blocks; signed animal-handling risk acknowledgement |
| Instructional team | Grooming, training and animal care instructors (technical) · Business instructor (PPC-BIZ panel with owner) · Personal readiness coach · Technology & AI lead |
| Required materials | Professional Dog Groomer Tools and Professional Dog Trainer Tools kits (catalog Section 9) · Owner-Operator Toolkit sanACAox accounts · laptop or tablet |
| Required texts | 11 core manuals; 70 reference and supplementary texts (Required & Reference Texts below) |
| Attendance policy | Clock hours are earned only for attended blocks. Minimum 95% attendance per term; missed lab hours are made up in Friday open lab within the same term. Below 90% at any checkpoint triggers a coach meeting and written plan. |
| Grading | Module: 10 activities + 10 micro-checks , 2 checkpoints and final quiz at ≥ 80%, capstone artifact accepted. Program: Competency Rubric at Competent on every row (catalog Section 9); safety-critical rows are pass/fail. |
| Safety gates | PPC-105, PPC-201, PPC-306, PPC-403, PPC-405, PPC-410 signed off before live-animal work; CPR/First Aid before practicum |
| Completion requirements | All 172 modules · 1,500 clock hours recorded · rubric Competent · PPC-BIZ capstone passed by panel · practicum log signed |
| Stacks into | Terminal credential |

## Term Outline

| Term | Technical modules | Business & personal modules | Applied | Hrs: tech / biz / applied | Term hours |
| --- | --- | --- | --- | --- | --- |
| Term 1 — Foundation | PPC-101, PPC-102, PPC-103, PPC-104, PPC-105, PPC-106 | 36 modules: LSH 101–105, PER 101–105, BUS 101–106, MKT 101–105, TEC 101–105, FIN 101–105, LEG 101–105 | — | 115 / 216 / 0 | 331 (≈12 wk) |
| Term 2 — Core Skill | PPC-201, PPC-202, PPC-203, PPC-204, PPC-205 | 36 modules: LSH 201–205, PER 201–205, BUS 201–206, MKT 201–205, TEC 201–205, FIN 201–205, LEG 201–205 | — | 170 / 216 / 0 | 386 (≈13 wk) |
| Term 3 — Advanced Skill | PPC-301, PPC-302, PPC-303, PPC-304, PPC-305, PPC-306 | 36 modules: LSH 301–305, PER 301–305, BUS 301–306, MKT 301–305, TEC 301–305, FIN 301–305, LEG 301–305 | — | 225 / 216 / 0 | 441 (≈15 wk) |
| Term 4 — Capstone | PPC-401, PPC-402, PPC-403, PPC-404, PPC-405, PPC-406, PPC-407, PPC-408, PPC-409, PPC-410 | 36 modules: LSH 401–405, PER 401–405, BUS 401–406, MKT 401–405, TEC 401–405, FIN 401–405, LEG 401–405 | PPC-BIZ | 90 / 216 / 36 | 342 (≈12 wk) |
| Program total |  |  |  | 600 / 864 / 36 | 1,500 (≈50 wk) |

## Week-by-Week Schedule

Hours column = technical / business & personal clock hours per week. "(cont.)" = module continues into the next week. Quizzes are taken in the week a module closes; level checkpoints and rubric reviews close each term.

| Week | Term | Technical modules | Business & personal modules | Hrs | Assessments this week |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | T1 Foundation | PPC‑101 (cont.) | LSH‑101, LSH‑102, LSH‑103 | 10 / 18 | Quizzes: LSH‑101, LSH‑102, LSH‑103 |
| Wk 2 | T1 Foundation | PPC‑101, PPC‑102 (cont.) | LSH‑104, LSH‑105, PER‑101 | 10 / 18 | Quizzes: PPC‑101, LSH‑104, LSH‑105, PER‑101 |
| Wk 3 | T1 Foundation | PPC‑102 (cont.) | PER‑102, PER‑103, PER‑104 | 10 / 18 | Quizzes: PER‑102, PER‑103, PER‑104 |
| Wk 4 | T1 Foundation | PPC‑102, PPC‑103 (cont.) | PER‑105, BUS‑101, BUS‑102 | 10 / 18 | Quizzes: PPC‑102, PER‑105, BUS‑101, BUS‑102 |
| Wk 5 | T1 Foundation | PPC‑103, PPC‑104 (cont.) | BUS‑103, BUS‑104, BUS‑105 | 10 / 18 | Quizzes: PPC‑103, BUS‑103, BUS‑104, BUS‑105 |
| Wk 6 | T1 Foundation | PPC‑104 (cont.) | BUS‑106, MKT‑101, MKT‑102 | 10 / 18 | Quizzes: BUS‑106, MKT‑101, MKT‑102 |
| Wk 7 | T1 Foundation | PPC‑104, PPC‑105 (cont.) | MKT‑103, MKT‑104, MKT‑105 | 10 / 18 | Quizzes: PPC‑104, MKT‑103, MKT‑104, MKT‑105 |
| Wk 8 | T1 Foundation | PPC‑105 (cont.) | TEC‑101, TEC‑102, TEC‑103 | 10 / 18 | Quizzes: TEC‑101, TEC‑102, TEC‑103 |
| Wk 9 | T1 Foundation | PPC‑105 (cont.) | TEC‑104, TEC‑105, FIN‑101 | 10 / 18 | Quizzes: TEC‑104, TEC‑105, FIN‑101 |
| Wk 10 | T1 Foundation | PPC‑105, PPC‑106 (cont.) | FIN‑102, FIN‑103, FIN‑104 | 10 / 18 | Quizzes: PPC‑105, FIN‑102, FIN‑103, FIN‑104 |
| Wk 11 | T1 Foundation | PPC‑106 (cont.) | FIN‑105, LEG‑101, LEG‑102 | 10 / 18 | Quizzes: FIN‑105, LEG‑101, LEG‑102 |
| Wk 12 | T1 Foundation | PPC‑106 | LEG‑103, LEG‑104, LEG‑105 | 10 / 18 | Quizzes: PPC‑106, LEG‑103, LEG‑104, LEG‑105 · Level checkpoint · rubric review |
| Wk 13 | T2 Core Skill | PPC‑201 (cont.) | LSH‑201, LSH‑202, LSH‑203 (cont.) | 13 / 17 | Quizzes: LSH‑201, LSH‑202 |
| Wk 14 | T2 Core Skill | PPC‑201, PPC‑202 (cont.) | LSH‑203, LSH‑204, LSH‑205, PER‑201 (cont.) | 13 / 17 | Quizzes: PPC‑201, LSH‑203, LSH‑204, LSH‑205 |
| Wk 15 | T2 Core Skill | PPC‑202 (cont.) | PER‑201, PER‑202, PER‑203, PER‑204 (cont.) | 13 / 17 | Quizzes: PER‑201, PER‑202, PER‑203 |
| Wk 16 | T2 Core Skill | PPC‑202, PPC‑203 (cont.) | PER‑204, PER‑205, BUS‑201, BUS‑202 (cont.) | 13 / 17 | Quizzes: PPC‑202, PER‑204, PER‑205, BUS‑201 |
| Wk 17 | T2 Core Skill | PPC‑203 (cont.) | BUS‑202, BUS‑203, BUS‑204 (cont.) | 13 / 17 | Quizzes: BUS‑202, BUS‑203 |
| Wk 18 | T2 Core Skill | PPC‑203 (cont.) | BUS‑204, BUS‑205, BUS‑206, MKT‑201 (cont.) | 13 / 17 | Quizzes: BUS‑204, BUS‑205, BUS‑206 |
| Wk 19 | T2 Core Skill | PPC‑203, PPC‑204 (cont.) | MKT‑201, MKT‑202, MKT‑203, MKT‑204 (cont.) | 13 / 17 | Quizzes: PPC‑203, MKT‑201, MKT‑202, MKT‑203 |
| Wk 20 | T2 Core Skill | PPC‑204 (cont.) | MKT‑204, MKT‑205, TEC‑201, TEC‑202 (cont.) | 13 / 17 | Quizzes: MKT‑204, MKT‑205, TEC‑201 |
| Wk 21 | T2 Core Skill | PPC‑204 (cont.) | TEC‑202, TEC‑203, TEC‑204 (cont.) | 13 / 17 | Quizzes: TEC‑202, TEC‑203 |
| Wk 22 | T2 Core Skill | PPC‑204, PPC‑205 (cont.) | TEC‑204, TEC‑205, FIN‑201, FIN‑202 (cont.) | 13 / 17 | Quizzes: PPC‑204, TEC‑204, TEC‑205, FIN‑201 |
| Wk 23 | T2 Core Skill | PPC‑205 (cont.) | FIN‑202, FIN‑203, FIN‑204, FIN‑205 (cont.) | 13 / 17 | Quizzes: FIN‑202, FIN‑203, FIN‑204 |
| Wk 24 | T2 Core Skill | PPC‑205 (cont.) | FIN‑205, LEG‑201, LEG‑202, LEG‑203 (cont.) | 13 / 17 | Quizzes: FIN‑205, LEG‑201, LEG‑202 |
| Wk 25 | T2 Core Skill | PPC‑205 | LEG‑203, LEG‑204, LEG‑205 | 13 / 17 | Quizzes: PPC‑205, LEG‑203, LEG‑204, LEG‑205 · Level checkpoint · rubric review |
| Wk 26 | T3 Advanced Skill | PPC‑301 (cont.) | LSH‑301, LSH‑302, LSH‑303 (cont.) | 15 / 14 | Quizzes: LSH‑301, LSH‑302 |
| Wk 27 | T3 Advanced Skill | PPC‑301, PPC‑302 (cont.) | LSH‑303, LSH‑304, LSH‑305 (cont.) | 15 / 14 | Quizzes: PPC‑301, LSH‑303, LSH‑304 |
| Wk 28 | T3 Advanced Skill | PPC‑302 | LSH‑305, PER‑301, PER‑302, PER‑303 (cont.) | 15 / 14 | Quizzes: PPC‑302, LSH‑305, PER‑301, PER‑302 |
| Wk 29 | T3 Advanced Skill | PPC‑303 (cont.) | PER‑303, PER‑304, PER‑305 (cont.) | 15 / 14 | Quizzes: PER‑303, PER‑304 |
| Wk 30 | T3 Advanced Skill | PPC‑303 | PER‑305, BUS‑301, BUS‑302 | 15 / 14 | Quizzes: PPC‑303, PER‑305, BUS‑301, BUS‑302 |
| Wk 31 | T3 Advanced Skill | PPC‑304 (cont.) | BUS‑303, BUS‑304, BUS‑305 (cont.) | 15 / 14 | Quizzes: BUS‑303, BUS‑304 |
| Wk 32 | T3 Advanced Skill | PPC‑304, PPC‑305 (cont.) | BUS‑305, BUS‑306, MKT‑301 (cont.) | 15 / 14 | Quizzes: PPC‑304, BUS‑305, BUS‑306 |
| Wk 33 | T3 Advanced Skill | PPC‑305 (cont.) | MKT‑301, MKT‑302, MKT‑303, MKT‑304 (cont.) | 15 / 14 | Quizzes: MKT‑301, MKT‑302, MKT‑303 |
| Wk 34 | T3 Advanced Skill | PPC‑305 (cont.) | MKT‑304, MKT‑305, TEC‑301 (cont.) | 15 / 14 | Quizzes: MKT‑304, MKT‑305 |
| Wk 35 | T3 Advanced Skill | PPC‑305 (cont.) | TEC‑301, TEC‑302, TEC‑303 | 15 / 14 | Quizzes: TEC‑301, TEC‑302, TEC‑303 |
| Wk 36 | T3 Advanced Skill | PPC‑305 (cont.) | TEC‑304, TEC‑305, FIN‑301 (cont.) | 15 / 14 | Quizzes: TEC‑304, TEC‑305 |
| Wk 37 | T3 Advanced Skill | PPC‑305 (cont.) | FIN‑301, FIN‑302, FIN‑303 (cont.) | 15 / 14 | Quizzes: FIN‑301, FIN‑302 |
| Wk 38 | T3 Advanced Skill | PPC‑305 (cont.) | FIN‑303, FIN‑304, FIN‑305, LEG‑301 (cont.) | 15 / 14 | Quizzes: FIN‑303, FIN‑304, FIN‑305 |
| Wk 39 | T3 Advanced Skill | PPC‑305 (cont.) | LEG‑301, LEG‑302, LEG‑303 (cont.) | 15 / 14 | Quizzes: LEG‑301, LEG‑302 |
| Wk 40 | T3 Advanced Skill | PPC‑305, PPC‑306 | LEG‑303, LEG‑304, LEG‑305 | 15 / 14 | Quizzes: PPC‑305, PPC‑306, LEG‑303, LEG‑304, LEG‑305 · Level checkpoint · rubric review |
| Wk 41 | T4 Capstone | PPC‑401, PPC‑402, PPC‑403, PPC‑404, PPC‑405 (cont.) | LSH‑401, LSH‑402, LSH‑403, LSH‑404 (cont.) | 8 / 21 | Quizzes: PPC‑401, PPC‑402, PPC‑403, PPC‑404, LSH‑401, LSH‑402, LSH‑403 |
| Wk 42 | T4 Capstone | PPC‑405, PPC‑406 (cont.) | LSH‑404, LSH‑405, PER‑401, PER‑402 | 8 / 21 | Quizzes: PPC‑405, LSH‑404, LSH‑405, PER‑401, PER‑402 |
| Wk 43 | T4 Capstone | PPC‑406, PPC‑407, PPC‑408 (cont.) | PER‑403, PER‑404, PER‑405, BUS‑401 (cont.) | 8 / 21 | Quizzes: PPC‑406, PPC‑407, PER‑403, PER‑404, PER‑405 |
| Wk 44 | T4 Capstone | PPC‑408, PPC‑409 (cont.) | BUS‑401, BUS‑402, BUS‑403, BUS‑404 | 8 / 21 | Quizzes: PPC‑408, BUS‑401, BUS‑402, BUS‑403, BUS‑404 |
| Wk 45 | T4 Capstone | PPC‑409 (cont.) | BUS‑405, BUS‑406, MKT‑401, MKT‑402 (cont.) | 8 / 21 | Quizzes: BUS‑405, BUS‑406, MKT‑401 |
| Wk 46 | T4 Capstone | PPC‑409 (cont.) | MKT‑402, MKT‑403, MKT‑404, MKT‑405 | 8 / 21 | Quizzes: MKT‑402, MKT‑403, MKT‑404, MKT‑405 |
| Wk 47 | T4 Capstone | PPC‑409 (cont.) | TEC‑401, TEC‑402, TEC‑403, TEC‑404 (cont.) | 8 / 21 | Quizzes: TEC‑401, TEC‑402, TEC‑403 |
| Wk 48 | T4 Capstone | PPC‑409 (cont.) | TEC‑404, TEC‑405, FIN‑401, FIN‑402 | 8 / 21 | Quizzes: TEC‑404, TEC‑405, FIN‑401, FIN‑402 |
| Wk 49 | T4 Capstone | PPC‑409 (cont.) | FIN‑403, FIN‑404, FIN‑405, LEG‑401 (cont.) | 8 / 21 | Quizzes: FIN‑403, FIN‑404, FIN‑405 |
| Wk 50 | T4 Capstone | PPC‑409 (cont.) | LEG‑401, LEG‑402, LEG‑403, LEG‑404 | 8 / 21 | Quizzes: LEG‑401, LEG‑402, LEG‑403, LEG‑404 |
| Wk 51 | T4 Capstone | PPC‑409, PPC‑410 (cont.) | LEG‑405, PPC‑BIZ (cont.) | 8 / 21 | Quizzes: PPC‑409, LEG‑405 |
| Wk 52 | T4 Capstone | PPC‑410 | PPC‑BIZ | 8 / 21 | Quizzes: PPC‑410, PPC‑BIZ · Level checkpoint · rubric review · Capstone panel · practicum sign-off |

## Assessment Calendar

| Point | When | Instrument | Pass standard |
| --- | --- | --- | --- |
| Module quizzes and checkpoints | Week each module closes (see schedule) | Final quiz + 2 checkpoints + capstone artifact | ≥ 80%; artifact accepted |
| Level checkpoint 1 | Last week of Term 1 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 2 | Last week of Term 2 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 3 | Last week of Term 3 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Level checkpoint 4 | Last week of Term 4 | Competency Rubric rows for that level; attendance audit | Competent on all rows; ≥ 95% attendance |
| Safety-critical sign-off | Before first live-animal service | Instructor checklist (handling, sanitation, CPR/First Aid) | Pass/fail |
| Practicum | Final term | Supervised practicum log | Minimums met and supervisor signature |
| Applied business capstone | Final week — PPC-BIZ | Instructor + owner panel | Launch plan, price menu, licensing/insurance worksheet, 90-day calendar accepted |

## Required & Reference Texts

| ID | Title | Author / publisher | Type |
| --- | --- | --- | --- |
| MAN‑IPDG | Professional Dog Groomer (merged: v1 200 hr + v2 300 hr + PPC grooming track) | Leashed program manual | Core manual |
| MAN‑PDT | Professional Dog Trainer | Leashed program manual | Core manual |
| MAN‑PPS | Professional Pet PPSitter | Leashed program manual | Core manual |
| MAN‑CAT | Professional Cat Groomer | Leashed program manual | Core manual |
| MAN‑LSH | Life Skills & Personal Readiness | Leashed program manual | Core manual |
| MAN‑BUS | Business & Leadership: Ownership, Operations & Expansion (merged BUS + LDR) | Leashed program manual | Core manual |
| MAN‑PER | Personal MaSittery & Lifelong Growth | Leashed program manual | Core manual |
| MAN‑MKT | Marketing, Branding & SEO MaSittery | Leashed program manual | Core manual |
| MAN‑TEC | AI & Technology Systems | Leashed program manual | Core manual |
| MAN‑FIN | Financial MaSittery, Bookkeeping & Tax Strategy | Leashed program manual | Core manual |
| MAN‑LEG | Legal, Risk, Compliance & Ethical Governance | Leashed program manual | Core manual |
| REF‑GRM‑01 | Dog Grooming for Beginners | Jorge Bendersky | Reference text · Book |
| REF‑GRM‑02 | Grooming Manual for Dog and Cat | — | Reference text · DOCX manuscript |
| REF‑GRM‑03 | The Everything Dog Grooming Book | — | Reference text · DOCX manuscript |
| REF‑BEH‑01 | HanACAook of Applied Dog Behavior and Training, Vol. 3 | Steven R. Lindsay | Reference text · Book |
| REF‑GRM‑04 | The Stone Guide to Dog Grooming for All Breeds | Ben Stone | Reference text · Book |
| REF‑TRN‑01 | Nate Schoemer's Dog Training Manual | — | Reference text · Book |
| REF‑PPS‑01 | Pet Care Givers and Families | — | Reference text · Book |
| REF‑HLTH‑01 | National Geographic Guide to Pet Health, Behavior, and Happiness | — | Reference text · Book |
| REF‑MED‑01 | Small Animal Critical Care Medicine | — | Reference text · Book |
| REF‑AI‑01 | AI for Animals: Revolutionizing Veterinary Care | Amelia Hawkins | Supplementary text · Book |
| REF‑ANI‑01 | Beastly: The 40,000-Year Story of Animals and Us | — | Supplementary text · Book |
| REF‑CARE‑01 | Knack Dog Care and Training | — | Reference text · Book |
| REF‑BIZ‑01 | Business Cycles | Francis X. Diebold | Supplementary text · Book |
| REF‑BIZ‑02 | Building a Successful Business | Dominik Mikulaschek | Reference text · Book |
| REF‑BIZ‑03 | The Disruptors | Sally Percy | Supplementary text · Book |
| REF‑BIZ‑04 | Go It Alone! | Bruce Judson | Reference text · Book |
| REF‑BIZ‑05 | The Successful Entrepreneur Playbook | Paul H. Woodruff | Reference text · Book |
| REF‑BIZ‑06 | 4-Hour Work Day | — | Supplementary text · Book |
| REF‑BIZ‑07 | The Business Bible | — | Reference text · Book |
| REF‑BIZ‑08 | Poverty Traps | Samuel Bowles | Supplementary text · Book |
| REF‑LDR‑01 | Leadership Presence | Belle Linda Halpern | Reference text · Book |
| REF‑LDR‑02 | Leadership and Ethics | Jacqueline Boaks | Reference text · Book |
| REF‑MKT‑01 | Multi-Channel Marketing, Branding and Retail Design | — | Reference text · Book |
| REF‑MKT‑02 | Marketing is not Rocket Science | — | Reference text · Book |
| REF‑MKT‑03 | Unconscious Branding | Douglas Van Praet | Supplementary text · Book |
| REF‑MKT‑04 | Content Branding Solutions for Entrepreneur Strategic Content Marketing | Peter Lucking | Reference text · Book |
| REF‑MKT‑05 | Branding: What You Need to Know About Building a Personal Brand… | — | Reference text · Book |
| REF‑MKT‑06 | Business Branding Guide | — | Reference text · Book |
| REF‑MKT‑07 | Salon Marketing | — | Reference text · Book |
| REF‑CX‑01 | Customer Service in Health Care | Kristin Baird | Reference text · Book |
| REF‑CX‑02 | Can Your Customer Service Do This? | — | Reference text · Book |
| REF‑CX‑03 | Crushing the Competition with Service | — | Reference text · Book |
| REF‑CX‑04 | Customer Service Is Just Foreplay | Jason D. Cass | Supplementary text · Book |
| REF‑FIN‑01 | J.K. Lasser's Small Business Taxes 2025 | — | Reference text · Book |
| REF‑FIN‑02 | Tax Accounting: A Guide for Small Business Owners | — | Reference text · Book |
| REF‑FIN‑03 | Small Time Operator | — | Reference text · Book |
| REF‑FIN‑04 | 475 Tax Deductions for All Small Businesses | — | Reference text · Book |
| REF‑LEG‑01 | Cybersecurity: Ethics, Legal, Risks | Ishaani Priyadarshini | Reference text · Book |
| REF‑LEG‑02 | The Tax and Legal Playbook | Mark J. Kohler | Reference text · Book |
| REF‑LEG‑03 | Reimagining Fairness: Equity, Cultural DiverPPSy, and Inclusion Competency Approach | — | Reference text · Book |
| REF‑LEG‑04 | PCI Compliance | Dr. Branden R. Williams | Reference text · Book |
| REF‑LEG‑05 | The Guide to OSHA Compliance | Robert D. Peterson | Reference text · Book |
| REF‑LEG‑06 | Security-First Compliance for Small Businesses | — | Reference text · Book |
| REF‑LEG‑07 | Transfer Pricing: Rules, Compliance and Controversy | — | Supplementary text · Book |
| REF‑LEG‑08 | Stop Harming Customers: A Compliance Manifesto | David Silverman | Reference text · Book |
| REF‑LEG‑09 | Tools of Effective Compliance | Thomas Schneider | Reference text · Book |
| REF‑LSH‑01 | Teaching life skills in intermediate phase | — | Reference text · Book |
| REF‑LSH‑02 | Stuff Students Should Know: Learn Essential Life Skills | — | Reference text · Book |
| REF‑LSH‑03 | 10 Proven Ways to Relieve Stress Now | — | Supplementary text · Book |
| REF‑LSH‑04 | Personal Finance | — | Reference text · Book |
| REF‑PER‑01 | The Personal MBA | Josh Kaufman | Reference text · Book |
| REF‑PER‑02 | Self-Talk Your Way to Success | Kam Knight | Reference text · Book |
| REF‑PER‑03 | Are You Ready to Succeed? | — | Reference text · Book |
| REF‑PER‑04 | Trigger High Performance | — | Reference text · Book |
| REF‑PER‑05 | Rebuilding Relationships in Recovery | — | Reference text · Book |
| REF‑PER‑06 | Trust Yourself: Stop Overthinking and Channel Your Emotions for Success at Work | — | Reference text · Book |
| REF‑AI‑02 | LinkedIn Personal Branding and Marketing | — | Reference text · Book |
| REF‑AI‑03 | The Marketing Mindset: 100 ChatGPT Prompts | — | Reference text · Book |
| REF‑AI‑04 | Enterprise AI | Shazia Sadiq | Reference text · Book |
| REF‑AI‑05 | AI In Finance | Krishan Arora | Reference text · Book |
| REF‑AI‑06 | AI Timekeeper | Robert Breeser | Reference text · Book |
| REF‑AI‑07 | AI Profit Hacks | — | Reference text · Book |
| REF‑AI‑08 | AI Startup Strategy | Adhiguna Mahendra | Reference text · Book |
| REF‑AI‑09 | AI and the Boardroom | Rohan Sharma | Reference text · Book |
| REF‑AI‑10 | Foundations of Agentic AI for Retail | — | Reference text · Book |
| REF‑AI‑11 | Retail 4.0: How AI is Shaping the Future of Shopping | — | Supplementary text · Book |
| REF‑AI‑12 | AI-Powered Accounting with Excel and Power BI | — | Reference text · Book |
| REF‑AI‑13 | The AI Revolution in Customer Service | — | Reference text · Book |
| REF‑AI‑14 | Natural Language Processing with Python: Building your Own Customer Service ChatBot | — | Reference text · Book |
| REF‑AI‑15 | Teaching and Learning in the Age of Generative AI | — | Reference text · Book |

# Part C — Instructor & Platform Sources

## C1. Instructor and Platform-Facing Sources (SYS)

Not learner-retrievable. Used for instructor training, LMS build, platform operations and school-level tax or governance questions.

| ID | Title | Author / publisher | Use | RAG role | Safety flag |
| --- | --- | --- | --- | --- | --- |
| REF‑SYS‑01 | Quantum Computational AI | Long Cheng Ph.D. | Platform, instructor training, LMS build | supplementary | No |
| REF‑SYS‑02 | Tax Planning and Compliance for Tax-Exempt Organizations | Jody Blazek | Platform + LEG, FIN instructors | reference | Yes (nonprofit tax) |
| REF‑SYS‑03 | Telling Ain't Training | Harold D. Stolovitch | Platform, instructor training, LMS build | core | No |
| REF‑SYS‑04 | Teaching with AI: A Practical Guide to a New Era of Human Learning | — | Platform, instructor training, LMS build | core | No |
| REF‑SYS‑05 | Transforming Teaching With Generative AI | — | Platform, instructor training, LMS build | core | No |
| REF‑SYS‑06 | Full Stack Web Development with Django and Vue (LMS with REST APIs and Kubernetes) | — | Platform, instructor training, LMS build | core | No |
| REF‑SYS‑07 | The Portable Lawyer for Mental Health Professionals | — | Platform + LEG instructors | reference | Yes (legal, senPPSive) |

## C2. Core Program Manuals — Build Status

| Manual | Covers | Status |
| --- | --- | --- |
| MAN-IPDG Professional Dog Groomer | IPDG technical core (merged); PPC grooming modules | Merge v1, v2 and PPC-GRM manuals into one; add IPDG-401 practicum chapter |
| MAN-PDT Professional Dog Trainer | PDT technical core; PPC training modules | Unchanged |
| MAN-ACA Bather–Animal Care Assistant | ACA technical core | Unchanged |
| MAN-PPS Professional Pet PPSitter | PPS technical core; PPC-401–403 | Remove PPS-103 chapter (moved to PPS-BIZ) |
| MAN-CAT Professional Cat Groomer | CAT technical core; PPC-404–407 | Unchanged |
| MAN-LSH Life Skills & Personal Readiness | LSH-101…405 | Author M01–M10 lesson content |
| MAN-BUS Business & Leadership | BUS-101…406 (merged BUS + LDR) | Merge MAN-BUS and legacy LDR content per catalog Appendix A |
| MAN-PER, MAN-MKT, MAN-TEC, MAN-FIN, MAN-LEG | PER, MKT, TEC, FIN, LEG families | Unchanged |
| Applied capstone guides (NEW) | GRM-BIZ, TRN-BIZ, ACA-BIZ, PPS-BIZ, CAT-BIZ, PPC-BIZ | Author one short guide per pathway using the M01–M10 sequences in the catalog |

# Appendix — Instructor Review Sign-Off

after reviewing the Leashed Integrated Course Catalog v3.2 and this guide. Approved items are issued as catalog v3.3.

| Reviewer role | Name | Sections reviewed | Decision (Approve / Revise) | Notes | Signature / date |
| --- | --- | --- | --- | --- | --- |
| Grooming instructor |  | Catalog 3, 7, 8, App. B; Guide B1, B5, B6 |  |  |  |
| Training instructor |  | Catalog 4, 8; Guide B2, B6 |  |  |  |
| Animal care instructor |  | Catalog 5, 6, 9; Guide B3, B4 |  |  |  |
| Business instructor |  | Catalog 3–8 business rows, bibliographies; Guide A, B |  |  |  |
| Personal readiness coach |  | Catalog 3–8 personal rows; Guide A5, B |  |  |  |
| Technology & AI lead |  | Catalog 11; Guide A9, C1 |  |  |  |
| Director / registrar |  | Catalog 1, 2; Guide A2–A8 |  |  |  |
| Owner (final approval) |  | All |  |  |  |